# A surfboard for the 21st century: eco-materials research and development by materials students

# Group members

Arnaud Marmier

Andrew French

Mike Sloan

Holi Harvey

# Introduction

The aim of this project is to increase the enthusiasm of students for material science by combining two attractive and topical subjects: surfing and sustainability.

In order to do so, we are developing four practicals. These practicals focus on the following problem: “as traditional surfboard materials are essentially petrochemicals, let’s look at replacing them by environmentally friendlier, mostly natural, alternatives”.

These practicals are aimed at 3rd year students.

The first two practicals consider the skin (traditionally glass-fibre cloth and epoxy or polyester resin) and consider replacement of either the cloth and/or the resin by natural alternatives. The first practical consists in laminating two test samples, a standard one (glass/epoxy) and an “eco” one. In the second practical, the student test their samples, tensile testing, ageing, and water adsorption.

The next two practicals investigate foam core (traditionally polyurethane or polystyrene) replacement, either by foams based on natural polymers, or by honeycombs type cardboard panels. The third practical consists in sourcing foam samples or manufacturing honeycomb out of materials amenable to sustainable production.

All the practicals have first a manufacturing component, i.e. make laminates or sandwich panels, followed by a testing component,

These practicals are be different from traditional lab based work: firstly they are mostly self guided (supported by videos of examples and extensive notes)and secondly the detail of the “designs” is left to the students. They will have to source sample of foams, design their own honeycomb, and select combinations of resins and fibres (chicken feathers and Polylactic acid? Have a go!). We want to tap into their creativity and inventiveness!

The following action plan details the documents that need to be produced to support the four tutorials.

Work Package 0: Module Description

Start Date: 14/07/10 Duration: 1 year+ End Date: 30/07/11 Task Leader: Arnaud Marmier (AM) Contributors: Andrew French (AF)

Work package Objectives - Produce a Handbook for the task (encapsulating the 4 practicals)

Description of Work - Identify practical issues (size of groups, timing …) - Write in a convenient handbook

Equipment and Facilities - None

Summary of Deliverables Ref; Title; Responsibility; Due Date; Comments. 0A; Task handbook; AM.

Dependences - Intro to Mech. Eng. Design task handbook, for consistency

Work Package 1: 1st Practical, Laminating

Start Date: 14/07/10 Duration: two weeks End Date: 30/07/10 Task Leader: Andrew French (AF) Contributors: Arnaud Marmier (AM)

Work package Objectives - Generate task sheet for 1st practical - Generate factsheets (FS) - Generate video “How-to” (Vid)

Description of Work - The first practical is based on laminating two 210*200 panels, one epoxy/glass, one “eco” - It is also used to introduce students to the language of composites, and to various examples of eco-composites (to generate ideas), and to bibliographic research - It is marked by a photo/video report and by inspection of two samples - It is followed by “2nd practical, testing of laminates”

Equipment and Facilities Facilities - Student workshop Equipment - H&S equipment from S21C (respirator) - Epoxy resin, UV-L resin - Glass cloth, 4 and 6 oz, Linen cloth, Other ????

Summary of Deliverables Ref; Title; Responsibility; Due Date; Comments. 1A; Task sheet (What, how, marking scheme); AM; 21/07/10. 1B; FS1: Online bibliography; AM; 23/07/10. 1C; Vid1: Online bibliography; AM; 30/07/10. 1D; FS2: Intro to composites; AF; ?. 1E; FS3: Eco-composites; AF; ?. 1F; FS4: How to laminate; AF; ?. 1G; Vid2: How to laminate; AF; ?. 1H; FS5: Generic H&S; AF; Not certain. 1I; FS6: Standards; AF; Not certain.

Dependences - “Surfing in the 21st century” (S21C) reports - S21C repository (www.4shared.com login: hk231@ex.ac.uk password: surfboard) - AF’s preliminary research

Work Package 2: 2nd Practical, Testing laminates

Start Date: 02/08/10 Duration: one weeks End Date: 07/08/10 Task Leader: Andrew French (AF) Contributors: Arnaud Marmier (AM)

Work package Objectives - Generate task sheet for 1st practical - Generate factsheets (FS) - Generate video “How-to” (Vid)

Description of Work - The second practical is based on testing the laminates produced in Pract1 - It is also used to introduce students to careful and thorough testing - It is marked by a very technical report (esp quality of results analysis) and by a “competition” (how good are the samples) - It is followed by “3rd practical, sourcing and testing of core material”

Equipment and Facilities Facilities - Student workshop - XAT Heavy Materials Laboratory, Room 123B, Harrison Equipment - Dog bone puncher - Tensile testing machine

Summary of Deliverables Ref; Title; Responsibility; Due Date; Comments. 2A; Draft Task Sheet (What, how, marking scheme); AM; 04/08/10. 2B; FS7: Tensile testing; AF; 03/08/10. 2C; Vid3: Tensile testing; AF; 03/08/10. 2D; FS8: Ageing; AF; 04/08/10. 2E; Vid4: Ageing; AF; 04/08/10. 2F; FS9: Water absorption; AF; 05/08/10. 2G; Vid5: Water absorption; AF; 05/08/10.

Dependences - WP1 (provides samples)

Work Package 3: Sourcing and testing of core material

Start Date: 09/08/10 Duration: 1 week End Date: 13/08/10 Task Leader: Andrew French (AF) Contributors: Arnaud Marmier (AM)

Work package Objectives - Generate task sheet for 3rd practical - Generate factsheets (FS) - Generate videos “How-to” (Vid)

Description of Work - The students are required to source/produce an eco core material, foam or - The core material should be subjected to compressive tests

Equipment and Facilities Facilities - Student workshop - XAT Heavy Materials Laboratory, Room 123B, Harrison Equipment - Band Saw - Lloyd Instruments EZ-20 testing machine

Summary of Deliverables Ref; Title; Responsibility; Due Date; Comments. 3A; Draft Task Sheet (What, how, marking scheme); AM; 09/08/10. 3B; FS10: Core Materials, Foam; AF; 10/08/10. 3C; Vid6: Compressive testing; AF; 12/08/10. 3D; FS11: Core Materials, Honeycomb; AF; 11/08/10. 3F; Vid7: Honeycomb; AF; 13/08/10.

Dependences - WP2 (testing background ?)

Work Package 4: Manufacture and test of Sandwich panels

Start Date: 09/08/10 Duration: 1 week End Date: 13/08/10 Task Leader: Andrew French (AF) Contributors: Arnaud Marmier (AM)

Work package Objectives - Generate task sheet for 4th practical - Generate factsheets (FS) - Generate videos “How-to” (Vid)

Description of Work - The material from WP3 is to be used in the construction of a sandwich panel *(FS- Sandwich Panels) in conjunction with the chosen eco-composite from WPs1&2 - Sandwich panels of uniform 10x10x120mm are subjected to flexural tests and to impact tests - It is marked by a very technical report (esp quality of results analysis) and by a “competition” (how good are the samples)

Equipment and Facilities Facilities - Student workshop - XAT Heavy Materials Laboratory, Room 123B, Harrison Equipment - Band Saw - Lloyd Instruments EZ-20 testing machine - Resil impactor

Summary of Deliverables Ref; Title; Responsibility; Due Date; Comments. 4A; Draft Task Sheet (What, how, marking scheme); AM. 4B; FS13: 3point bending test; AF. 4C; Vid8: 3point bending test; AF. 4D; FS14: Impact testing; AF. 4E; Vid9: Impact testing; AF.

Dependences - WP2 (testing background ?)

# Appendix A: List of Fact Sheets and Videos

Fact sheets

FS1: Online bibliography

FS2: Intro to composites

FS3: Eco-composites

FS4: How to laminate

FS5: Generic H&S

FS6: Standards

FS7: Tensile testing

FS8: Ageing

FS9: Water absorption

FS10: Core Materials, Foam

FS11: Core Materials, Honeycomb

FS12: 3point bending test

FS13: Impact testing

Videos

Vid1: Online bibliography

Vid2: How to laminate

Vid3: Tensile testing

Vid4: Ageing

Vid5: Water Adsorption

Vid6: Compressive testing

Vid7: Honeycomb

Vid8: 3point bending test

Vid9: Impact testing