## M-H
| MAIN |  |  | FEASIBILITY |  | DESIGN | PLANNING | IMPLEMENTATION |  | EVALUATION |  | OPTIONS | HELP
HOME |  | Welcome to the GOODwater Program
INTRO
GOODwater is divided into the 8 sections listed below. To begin using this program, click on the Intro link highlighted below in red. Experienced users can navigate to any section in the program from this page by clicking on the desired link.
SETUP
|  |  | Main Page | [5 empty] | Feasibility Assessment
|  |  | Home |  | This module serves as an introduction to the program. A navigation menu is provided to move to all the different sections. An explanation of how the program is used is found here. Initial project information can be entered here and will propagate throughout the different pages. |  |  |  | Home |  | This module enables the user to assess the feasibility of completing a gravity flow water supply system at a given site. A set of suggested actions are presented. Once these actions are completed the gathered information can be entered into the program, and a report is generated.
|  |  | !! Introduction !! | [5 empty] | Actions
|  |  | Setup | [5 empty] | Input
Site Report
|  |  | System Design | [5 empty] | Project Planning
|  |  | Home |  | This module assists engineers in creating a quality water supply system design. A set of suggested actions is presented to the user. A space is provided to enter topographical information and system components. A genetic algorithm is provided to produced a low cost configuration of pipe diameters for the entered topography and component layout. |  |  |  | Home |  | This module assists in preparing a budget for the proposed water system. The different materials needed for each component of the water system can be added, and prices can be set for each item. A itemized budget is then created for the water system.
|  |  | Actions | [5 empty] | Actions
|  |  | Topographic Info | [5 empty] | Components
|  |  | Add Components | [5 empty] | Materials
|  |  | Generate Design | [5 empty] | Budget
Design Report
|  |  | Project Implementation | [5 empty] | Project Evaluation
|  |  | Home |  | This module provides a space for project managers to create a project calendar. Information about when each part of the project is to be started and completed can be entered. The program then organizes the specific tasks to be completed and generates a project timeline. |  |  |  | Home |  | This module provides an evaluation of the projects sustainability. Each stage of the project is scored on a scale from 0 to 20. The five stages are summed for a score out of 100.
|  |  | Actions | [5 empty] | Actions
|  |  | Schedule | [5 empty] | Evaluation
Report
|  |  | Options | [5 empty] | Help
|  |  | Home |  | This Module contains different options available to users. Constants used throughout the program can be set at the 'Global Variables' page. At the 'Feasibility Coefficients' page, data for pricing estimates is entered. |  |  |  | Home |  | This Module provides assistance to users of the program. A summary of the different actions suggested throughout the different modules is presented. A summary of user inputs is also found here. A list of useful references is also included.
|  |  | Global Variables | [5 empty] | Actions
|  |  | Feasibility Coefficients | [5 empty] | Inputs
|  |  | Pipe Information | [5 empty] | Sources

## M-I
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Introduction To GOODwater
INTRO
The GOODwater file is a Microsoft Excel template. A template is a pre-formatted workbook which includes standard styles, formulas, macros and other settings. Each time the GOODwater template is opened, a blank project is presented, with the workbook ready to use. The template presents to users blank forms, checkboxes, navigation menus, and other objects, witch users fill in as a project progresses. Uses are are also presented with action buttons which when clicked perform calculations on the data entered into the workbook. The user begins a new project by entering data and settings into the blank template. When the user is ready to save, the project is saved under a new name using the “save as” command in Microsoft Excel. In this manner different projects are stored in their own unique excel file. Multiple versions of a project can be saved under different file names, and new projects can be started by opening the GOODwater template and starting a blank workbook.
SETUP
In order to calculate and automate the complex routines included within GOODwater, the software makes use of Macro routines and the Solver add-in. Macros are small programs written in the Visual Basic for Applications (VBA) programming language that can be run within Microsoft Excel. As such they can store commonly used complex functions and actions in a simple, easily to perform format. GOODwater uses macros to accomplish many of the more complex calculations needed to design water systems. In order to take advantage of the macros in GOODwater they need to be enabled. To enable macros, the “Macro Security Level” in Excel needs to be adjusted. If the level is set to High, the macros will not be able to run. The “Macro Security Level” can be changed in the Macro Setting tab of the trust center menu in Excel 2007. The Solver Add-In is a component of Excel developed by Frontline Systems, Inc and comes standard with excel, though is not loaded with the typical installation. The solver tool uses a generalized reduced gradient nonlinear optimization code to assists users with complex problems. To load the Solver Add-In, users must check the Solver box in the Manage Excel Add-In sub menu, found in the Add-In tab of the Excel Options menu. Once macros are enabled and the Solver add-in has been loaded, the GOODwater software is ready for use (Microsoft 2008, all).
GOODwater is a robust program dealing with many aspects of gravity fed water system projects. As such, there are many menus and submenus included within the workbook. Upon initialization of the program, the user encounters the Home page in the Main menu. The Home page contains a list of all the important pages to be found within the program. This page, like most pages in the software, is divided into three sections. The top most section includes the title of the program, information about the project if entered, and a bar of different menus. This bar is important for navigating throughout the workbook. Contained within the bar are eight options: Main, Feasibility, Design, Planning, Implementation, Evaluation, Options, and Help. Users can move to any of these sections in the program by clicking on the appropriate location in the navigation bar. When one of these sections is clicked, the user is directed to that module, and a sub-menu appears. The sub-menu is located on the left side of the sheet below the navigation bar, and is unique to each module’s features. Again, by clicking on the desired sub-menu option on the left, the user navigates to specific sheets addressing confined topics. In the center right of the sheet, below the navigation bar and to the right of the sub-menu area the substance of GOODwater is displayed. In this area the forms, options, checkboxes, descriptions, graphs, and reports of the program are displayed. This area also includes action buttons which, when clicked, manipulate the data entered into the program.
When GOODwater is opened, the Home page is displayed first. This page directs suggest that first time users navigate to the Introduction page. The Introduction page provides a summary of what the GOODwater software is designed for. This page is intended to introduce new users to the software and explain how it is to be used. The page includes an explanation of the menus and how to navigate between pages. A summary of how to enable macros and load the Solver add-in is also provided for first time users. Also included in this page is an action button. This is the first of many action buttons found in the software. These buttons are used to prompt the software to accomplish specific tasks. When clicked, the actions buttons call macros and evaluate or manipulate data entered into the workbook. Clicking an action button initiates a series of actions, and it is important to note that these can not be undone using the back or undo buttons in excel. After the Introduction page has been reviewed, first time users are directed to the Setup page.
RESET ALL

## M-S
| MAIN |  |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Setup: Project Information
INTRO
Fill in the blue tables as best able from regional data. The information will propagate throughout the program. Once completed, you can click on the section above that you want to work on.
SETUP
Project Information
Community Name
Community Municipality / County
Community State / Province
Country
Project Title
Engineer Name
Organization Name
Organization Address (line 1)
(line 2)
Reset Form

## F-H
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Feasibility Assessment
ACTIONS
The goal of GOODwater is to provide a clear methodology for managers to implement sustainabe gravity fed water system projects. Projects should begin with an assessment of possible project sites. Site assessment is an investigative process which typically begins with a request for assistance from a community or organization present in the region. A representative of the solicited organization should then visit the community to collect information (McConville and Mihelcic 2007). The desire for progress in the project, as well as participation of the community with the organizations to be involved, need to be evaluated at this time. Provincial development priorities, local skills and resources available, regional issues, environmental and monetary concerns should be assessed during this period (Deverill, Bibby, Wedgewood, and Smout 2002). These various considerations are addressed by the GOODwater software. Through use of the GOODwater program, managers can quickly generate standardized reports for different locations which can then be reviewed by decision makers. It is hoped that in this manner only projects meeting minimum criteria will be initiated.
INPUTS
REPORTS
RESET FEASIBILITY MODULE

## F-A
| MAIN |  |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION |  | OPTIONS | HELP
HOME |  | Feasibility Assessment: Suggested Actions
ACTIONS
|  | Below is a list of different actions to be undertaken to complete an assessment of a sites feasibility for a Gravity Flow Water System. Check the boxes for each action that has been completed and/or understood. | [6 empty] | NOTE: The Titles for each box are links to full descriptions of each table
INPUTS
REPORTS
Socio - Cultural Respect
Generate a yearly calendar of work and social life in the community.
Identify social preferences and traditional beliefs associated with water supply and sanitation practices.
Determine the level of health education in the community.
Recognize differences in gender roles in water and sanitation.
Community Participation
Conduct a participatory needs assessment at the local level to determine local development priorities.
Identify stakeholders and community leaders.
Determine the type of political organization and cohesion at the community level.
Reach a consensus with community members that project intervention is appropriate.
Political Cohesion
Conduct a situational analysis of regional and national issues, such as political structure and stability, government policies, and foreign aid.
Ensure that proposed project is consistent with regionally identified development priorities and plans.
Research the history of NGO and government projects in the area.
Establish communication lines with existing NGO and/or government institutions in the area.
Economic Sustainability
Understand the local and national economic situation (poverty level, employment, cost of living, flow of resources).
Understand how the community economic situation is affected by water and sanitation issues.
Identify sources of monetary and non-monetary resources (materials, labor, and tools) within the community.
Assess the community willingness-to-pay in both monetary and non-monetary terms for current water and sanitation services
Environmental Sustainability
Identify local resources for water and sanitation.
Collect data on climate and environmental constraints that will factor into project design.
Identify potential environmental concerns at the local and regional level.
Determine community understanding of environmental problems and the willingness to correct them.
Reset Form

## F-I
| MAIN |  |  | FEASIBILITY | DESIGN | PLANNING |  | IMPLEMENTATION |  | EVALUATION |  | OPTIONS | HELP
HOME |  | Feasibility Assessment: User Input
ACTIONS
Fill in the blue tables as best able from regional data. Once this has been complete click on the "GENERATE REPORT" button to view the results.
INPUTS
REPORTS
|  |  | Required Variables |  |  |  | Value |  | Units |  | notes
Variable Name
|  |  | Community Population | [5 empty] | #
|  |  | Water Source Type | [5 empty] | NA
|  |  | Number of Individual Sources to be used | [5 empty] | #
|  |  | Total Flow Rate From Sources to be Utilized | [5 empty] | (L/S)
|  |  | Source Elevation | [5 empty] | (m)
|  |  | Distance To Source | [5 empty] | (m)
|  |  | Network Length in Community | [5 empty] | (m)
|  |  | Highest Pt. Served In Community | [5 empty] | (m)
|  |  | Lowest Pt. Served In Community | [5 empty] | (m)
|  |  | Area Soil Type | [5 empty] | (man-days/m^3)
|  |  | Number of Days per Week Labors can work | [5 empty] | #
|  |  | Number of Months Per Year available for work | [5 empty] | #
|  |  | Monthly Community Contribution Per Family | [5 empty] | ($$)
|  |  | Total Funding Available For Project | [5 empty] | ($$)
GENERATE REPORT
RESET FORM

## F-R
BACK

## D-H
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | System Design
ACTIONS
In order to provide the appropriate level of service to water recipients, water systems must be designed using standard engineering principals. Due to the economic constraints often imposed while working in developing countries, it is important to be able to supply the desired service capacity at the least capital cost. Availability and costs of materials can differ greatly worldwide and it is important that the proposed system be designed with the most appropriate materials and technology for a given region. Gravity flow systems are many times located in mountainous regions, thus adding additional constraints of uneven topography which the designer must consider. By balancing demands for service, finical limits and topographical constraints the design module of GOODwater produces appropriate, technically sound designs for small scale rural water system project managers worldwide. One of the stated goals of the GOODwater software is to assist project managers in designing GFWS in the most economical manner. This requires selection of the optimum configuration of pipe diameters, while maintaining minimum and maximum pressure limits. Pipe diameters are discrete values because materials only come in specific sizes, and as such, optimization solutions for water supply networks are made up of non-continuous variables. Many different approaches have been proposed by engineers to deal with this difficult problem, with solutions falling into two categories. The first category refers to problems that split each link into sub-links who‟s lengths and diameters vary in accordance with the desired head loss in that section. Alperovits and Shamir, as well as many others have proposed methods for determining the best configuration for water supply networks using split pipe algorithms (Alperovits and Shamir 1977). The second category refers to optimization routines which assume that the pipes between two points will be of all one diameter. The solution to this problem is preferable as it does not lead to impractical configurations. For GOODwater only solutions of the second category are sought. Yates et al. proved in their 1984 paper that water system optimization problems of this category are NP-Hard, meaning that they belong to a class of mathematical problems for which no practical algorithm can be developed (Yates, Templeman, and Boffey 1984). In response to this situation, and the development of faster computer processing, many heuristic methods have been developed to address these problems. Heuristic methods, such as evolutionary optimization, genetic algorithms, simulated annealing, harmony search, and others, use iterative computational processes to develop an approximate solution. These methods offer advantages such as enabling pipe diameters to assume discrete values and including multiple objectives in the optimization process, and have been applied many times to the problem of water system optimization since their inception (Mays 1997). GOODwater uses a simple genetic algorithm (GA) to generated designs for water system designers. A genetic algorithm is a heuristic search method that mimics the evolutionary process found in nature. Figure 3.1 shows how a GA operates. In a typical GA an initial population of solutions is chosen from the solution space. This population of solutions is then evaluated for its fitness. Solutions are then selected proportionally according to their fitness, with better solutions having a higher probably of selection. Once selections are made the crossover process combines selected solutions to create new solutions. These new solutions are slightly mutated at random locations. If the stopping criterion has been achieved, the best solution is then offered to the user, if not, the process continues again at the evaluation step (Pham and Karaboga 2000).
TOPO INFO
COMPONETS
GENERATE
REPORT
Reset Design Module

## D-A
| MAIN |  |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION |  | OPTIONS | HELP
HOME |  | System Design: Suggested Actions
ACTIONS
|  | Below is a list of different actions to be undertaken to complete a design of a Gravity Flow Water System. Check the boxes for each action that has been completed and/or understood. | [6 empty] | NOTE: The Titles for each box are links to full descriptions of each table
TOPO INFO
COMPONETS
GENERATE
Socio - Cultural Respect
REPORT
Assess how the proposed interventions will affect daily activities and socio-cultural roles within the community.
Evaluate the willingness and capacity of the community to perform operation, maintenance, and disposal requirements for each design.
Design recognizes and respects traditional gender roles.
Recognize why biases exist towards certain technologies by donors and/or locals.
Community Participation
The project goals are clearly defined and understood by the community and development workers.
Identify a representative committee that can act as the community liaison throughout the project.
Present several technically feasible alternatives for community evaluation and feedback.
Community members formally select a design based on an understanding of the constraints involved in the selection process.
Political Cohesion
Develop a working relationship with partner organization(s), including at least one that is based in the host country.
Consult the plans and designs of other organizations on similar projects.
Explore options to integrate existing technologies or programs into conceptual designs.
Contact potential partner institutions for project financing.
Economic Sustainability
Estimate the implementation costs of each conceptual design.
Estimate operation, maintenance, and disposal costs for each conceptual design.'
Assess the community willingness-to-pay in both monetary and non-monetary terms for each improved system.
Conduct an economic feasibility assessment to evaluate long-term project viability based on cost estimates, projected operation and maintenance costs, community willingness to pay, the need for outside resources, and the availability of outside funding.
Environmental Sustainability
Assess the capacity for sustainable water use in the geographic area.
Consider how seasonal variation in water supply, demand, and environmental conditions will affect each conceptual design.
Consider land needs and availability of suitable land for each alternative.
Conduct a site impact analysis for each alternative.
Reset Form

## D-T
| MAIN |  |  |  | FEASIBILITY |  |  | DESIGN |  | PLANNING |  | IMPLEMENTATION |  |  | EVALUATION | [9 empty] | OPTIONS |  |  |  |  | HELP
HOME |  | System Design: Topography Information
ACTIONS
|  |  | Fill in the blue tables as best able from Topographical data. Once this has been complete click on the "ADD COMPONETS" button to continue. Please note that reaches must connect to an earlier reach, and no two reaches can start at the same point! | [17 empty] | NOTE: | [6 empty] | If you have many survey points they can be copied and truncated with the data input page located here.
TOPO INFO
COMPONETS
GENERATE |  |  | REACH |  |  |  | 1 |  |  |  | Points in Reach: |  | 25 | REACH | [7 empty] | 2 | [6 empty] | Points in Reach: |  | 25 | REACH | [7 empty] | 3 | [5 empty] | Points in Reach: | 4 | REACH | [7 empty] | 4 | [5 empty] | Points in Reach: | 4 | REACH | [7 empty] | 5 | [5 empty] | Points in Reach: | 6 | REACH | [7 empty] | 6 | [5 empty] | Points in Reach: | 21 | REACH | [7 empty] | 7 | [5 empty] | Points in Reach: | 9 | REACH | [7 empty] | 8 | [5 empty] | Points in Reach: | 8 | REACH | [7 empty] | 9 | [5 empty] | Points in Reach: | 25 | REACH | [7 empty] | 10 | [5 empty] | Points in Reach: | 3 | REACH | [7 empty] | 11 | [5 empty] | Points in Reach: | 11 | REACH | [7 empty] | 12 | [5 empty] | Points in Reach: | 3 | REACH | [7 empty] | 13 | [5 empty] | Points in Reach: | 4 | REACH | [7 empty] | 14 | [5 empty] | Points in Reach: | 6 | REACH | [7 empty] | 15 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 16 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 17 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 18 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 19 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 20 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 21 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 22 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 23 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 24 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 25 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 26 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 27 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 28 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 29 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 30 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 31 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 32 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 33 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 34 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 35 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 36 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 37 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 38 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 39 | [5 empty] | Points in Reach: | 0 | REACH | [7 empty] | 40 | [5 empty] | Points in Reach: | 0
[11 empty] | Reach Length: |  | 5254 | [15 empty] | Reach Length: |  | 7142 | [14 empty] | Reach Length: | 5553 | [14 empty] | Reach Length: | 5912 | [14 empty] | Reach Length: | 5972 | [14 empty] | Reach Length: | 6988 | [14 empty] | Reach Length: | 5766 | [14 empty] | Reach Length: | 5866 | [14 empty] | Reach Length: | 7479 | [14 empty] | Reach Length: | 6480 | [14 empty] | Reach Length: | 5978 | [14 empty] | Reach Length: | 6784 | [14 empty] | Reach Length: | 7010 | [14 empty] | Reach Length: | 7429 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0 | [14 empty] | Reach Length: | 0
REPORT |  |  | place name of reach here | [5 empty] | Start At Your highest source and move |  |  |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  |  | 1 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 2 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 3 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 4 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 5 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 6 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 7 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 8 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 9 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 10 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 11 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 12 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  | 13 | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach: |  |  | place name of reach here | [12 empty] | This Reach Connects To Reach:
[9 empty] | towards the farthest point from it | [17 empty] | At Point: |  |  |  | 25 | [13 empty] | At Point: |  | 25 | [13 empty] | At Point: |  | 4 | [13 empty] | At Point: |  | 4 | [13 empty] | At Point: |  | 6 | [13 empty] | At Point: |  | 21 | [13 empty] | At Point: |  | 9 | [13 empty] | At Point: |  | 8 | [13 empty] | At Point: |  | 25 | [13 empty] | At Point: |  | 3 | [13 empty] | At Point: |  | 11 | [13 empty] | At Point: |  | 3 | [13 empty] | At Point: |  | 4 | [13 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point: | [15 empty] | At Point:
|  |  | Point | Distance (m) |  | Elevation (m) |  |  | Notes |  |  |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes |  |  | Point | Distance (m) | [5 empty] | Elevation (m) | [5 empty] | Notes
|  |  | 1 | 0 |  | 450 | [7 empty] | 1 | 5254 | 0 | 0 | -329 | 0 | 0 | 329 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 | 7142 | 0 | 0 | -180.2022 | 0 | 0 | 180.2022 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 5553 | 0 | 0 | -311.1688 | 0 | 0 | 311.1688 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 5912 | 0 | 0 | -324.9483 | 0 | 0 | 324.9483 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 5972 | 0 | 0 | -291.7028 | 0 | 0 | 291.7028 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 6988 | 0 | 0 | -270.5692 | 0 | 0 | 270.5692 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 5766 | 0 | 0 | -298.2453 | 0 | 0 | 298.2453 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 5866 | 0 | 0 | -289.5537 | 0 | 0 | 289.5537 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 7479 | 0 | 0 | -153.7035 | 0 | 0 | 153.7035 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 6480 | 0 | 0 | -247 | 0 | 0 | 247 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 5978 | 0 | 0 | -200.5124 | 0 | 0 | 200.5124 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 6784 | 0 | 0 | -205.3173 | 0 | 0 | 205.3173 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 7010 | 0 | 0 | -210 | 0 | 0 | 210 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Connected | 0 | 0 | #VALUE! | 0 | 0 | Not Connected | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2 | 182 |  | 450 | [7 empty] | 2 | 5256 | [5 empty] | 328 | [10 empty] | 2 | 5489 | [5 empty] | 315.5086 | [8 empty] | 2 | 5870 | [5 empty] | 318.6195 | [8 empty] | 2 | 5841 | [5 empty] | 317.6427 | [8 empty] | 2 | 5350 | [5 empty] | 329.5012 | [8 empty] | 2 | 5583 | [5 empty] | 316.8542 | [8 empty] | 2 | 5760 | [5 empty] | 299.9829 | [8 empty] | 2 | 5360 | [5 empty] | 326 | [8 empty] | 2 | 6480 | [5 empty] | 247 | [8 empty] | 2 | 6635 | [5 empty] | 226.2129 | [8 empty] | 2 | 6784 | [5 empty] | 205.3173 | [8 empty] | 2 | 6974 | [5 empty] | 218 | [8 empty] | 2 | 7279 | [5 empty] | 163.5207
|  |  | 3 | 182.01 |  | 450 | [7 empty] | 3 | 5258 | [5 empty] | 327 | [10 empty] | 3 | 5553 | [5 empty] | 311.1688 | [8 empty] | 3 | 5912 | [5 empty] | 324.9483 | [8 empty] | 3 | 5891 | [5 empty] | 308.0308 | [8 empty] | 3 | 5432 | [5 empty] | 325.1878 | [8 empty] | 3 | 5613 | [5 empty] | 314.9794 | [8 empty] | 3 | 5779 | [5 empty] | 291.1607 | [8 empty] | 3 | 5432 | [5 empty] | 325.1878 | [8 empty] | 3 | 6480 | [5 empty] | 247 | [8 empty] | 3 | 6662 | [5 empty] | 224.0945 | [8 empty] | 3 | 6784 | [5 empty] | 205.3173 | [8 empty] | 3 | 7010 | [5 empty] | 210 | [8 empty] | 3 | 7329 | [5 empty] | 158.5837
|  |  | 4 | 833 |  | 405 | [7 empty] | 4 | 5354 | [5 empty] | 316.116 | [10 empty] | 4 | 5553 | [5 empty] | 311.1688 | [8 empty] | 4 | 5912 | [5 empty] | 324.9483 | [8 empty] | 4 | 5941 | [5 empty] | 297.7064 | [8 empty] | 4 | 5500 | [5 empty] | 323.5134 | [8 empty] | 4 | 5640 | [5 empty] | 315.6469 | [8 empty] | 4 | 5798 | [5 empty] | 284.7923 | [8 empty] | 4 | 5500 | [5 empty] | 323.5134 | [24 empty] | 4 | 6706 | [5 empty] | 222.6869 | [24 empty] | 4 | 7010 | [5 empty] | 210 | [8 empty] | 4 | 7379 | [5 empty] | 154.6607
|  |  | 5 | 853 |  | 405 | [7 empty] | 5 | 5474 | [5 empty] | 311.3595 | [42 empty] | 5 | 5972 | [5 empty] | 291.7028 | [8 empty] | 5 | 5576 | [5 empty] | 318.325 | [8 empty] | 5 | 5671 | [5 empty] | 315.8273 | [8 empty] | 5 | 5822 | [5 empty] | 288.3052 | [8 empty] | 5 | 5576 | [5 empty] | 318.325 | [24 empty] | 5 | 6751 | [5 empty] | 220.5932 | [40 empty] | 5 | 7429 | [5 empty] | 151.9714
|  |  | 6 | 990 |  | 426 | [7 empty] | 6 | 5543 | [5 empty] | 308.5722 | [42 empty] | 6 | 5972 | [5 empty] | 291.7028 | [8 empty] | 6 | 5633 | [5 empty] | 308.6 | [8 empty] | 6 | 5717 | [5 empty] | 304.5042 | [8 empty] | 6 | 5838 | [5 empty] | 289.8387 | [8 empty] | 6 | 5633 | [5 empty] | 308.6 | [24 empty] | 6 | 6801 | [5 empty] | 222.4109 | [40 empty] | 6 | 7429 | [5 empty] | 151.9714
|  |  | 7 | 1130 |  | 438 | [7 empty] | 7 | 5588 | [5 empty] | 305.4991 | [58 empty] | 7 | 5738 | [5 empty] | 296.3518 | [8 empty] | 7 | 5749 | [5 empty] | 302.5974 | [8 empty] | 7 | 5866 | [5 empty] | 289.5537 | [8 empty] | 7 | 5738 | [5 empty] | 296.3518 | [24 empty] | 7 | 6851 | [5 empty] | 218.9952
|  |  | 8 | 1588 |  | 421 | [7 empty] | 8 | 5621 | [5 empty] | 307.004 | [58 empty] | 8 | 5865 | [5 empty] | 288.9509 | [8 empty] | 8 | 5766 | [5 empty] | 298.2453 | [8 empty] | 8 | 5866 | [5 empty] | 289.5537 | [8 empty] | 8 | 5861 | [5 empty] | 298.2625 | [24 empty] | 8 | 5891 | [5 empty] | 211.2486
|  |  | 9 | 1996 |  | 376 | [7 empty] | 9 | 5673 | [5 empty] | 311.216 | [58 empty] | 9 | 6001 | [5 empty] | 281.1753 | [8 empty] | 9 | 5766 | [5 empty] | 298.2453 | [24 empty] | 9 | 5961 | [5 empty] | 275.565 | [24 empty] | 9 | 5938 | [5 empty] | 205.5398
|  |  | 10 | 1996.01 |  | 376 | [7 empty] | 10 | 5818 | [5 empty] | 315.7111 | [58 empty] | 10 | 6053 | [5 empty] | 285.9 | [40 empty] | 10 | 5961.01 | [5 empty] | 275.565 | [24 empty] | 10 | 5978 | [5 empty] | 200.5124
|  |  | 11 | 2268 |  | 316 | [7 empty] | 11 | 5820 | [5 empty] | 318.6195 | [58 empty] | 11 | 6053.01 | [5 empty] | 285.9 | [40 empty] | 11 | 6060 | [5 empty] | 260.7283 | [24 empty] | 11 | 5978 | [5 empty] | 200.5124
|  |  | 12 | 2281 |  | 317 | [7 empty] | 12 | 5822 | [5 empty] | 316.0407 | [58 empty] | 12 | 6185 | [5 empty] | 246 | [40 empty] | 12 | 6166 | [5 empty] | 261.2772
|  |  | 13 | 2337 |  | 334 | [7 empty] | 13 | 5943 | [5 empty] | 310.5 | [58 empty] | 13 | 6299 | [5 empty] | 274 | [40 empty] | 13 | 6258 | [5 empty] | 262.1556
|  |  | 14 | 2488 |  | 303 | [7 empty] | 14 | 6042 | [5 empty] | 301.0336 | [58 empty] | 14 | 6414 | [5 empty] | 269.1337 | [40 empty] | 14 | 6344 | [5 empty] | 251
|  |  | 15 | 2507 |  | 303 | [7 empty] | 15 | 6142 | [5 empty] | 302 | [58 empty] | 15 | 6539 | [5 empty] | 272.6453 | [40 empty] | 15 | 6435 | [5 empty] | 249.3801
|  |  | 16 | 2604 |  | 311 | [7 empty] | 16 | 6242 | [5 empty] | 283.2413 | [58 empty] | 16 | 6655 | [5 empty] | 263.6115 | [40 empty] | 16 | 6585 | [5 empty] | 248
|  |  | 17 | 3211 |  | 290 | [7 empty] | 17 | 6279 | [5 empty] | 279.5344 | [58 empty] | 17 | 6725 | [5 empty] | 252.23 | [40 empty] | 17 | 6685 | [5 empty] | 212.0059
|  |  | 18 | 3813 |  | 257 | [7 empty] | 18 | 6279.01 | [5 empty] | 279.5344 | [58 empty] | 18 | 5804 | [5 empty] | 239.4453 | [40 empty] | 18 | 6756 | [5 empty] | 199.6
|  |  | 19 | 4096 |  | 243 | [7 empty] | 19 | 6357 | [5 empty] | 269 | [58 empty] | 19 | 5897 | [5 empty] | 255.8913 | [40 empty] | 19 | 6756.01 | [5 empty] | 199.6
|  |  | 20 | 4225 |  | 254 | [7 empty] | 20 | 6406 | [5 empty] | 264.5678 | [58 empty] | 20 | 6988 | [5 empty] | 270.5692 | [40 empty] | 20 | 6835 | [5 empty] | 188.7047
|  |  | 21 | 4537 |  | 281 | [7 empty] | 21 | 6445 | [5 empty] | 256.8 | [58 empty] | 21 | 6988 | [5 empty] | 270.5692 | [40 empty] | 21 | 6975 | [5 empty] | 179.4703
|  |  | 22 | 4974 |  | 291 | [7 empty] | 22 | 6527 | [5 empty] | 241.832 | [106 empty] | 22 | 7095 | [5 empty] | 180.4011
|  |  | 23 | 5132 |  | 330 | [7 empty] | 23 | 6582 | [5 empty] | 234 | [106 empty] | 23 | 7219 | [5 empty] | 168.9597
|  |  | 24 | 5201 |  | 340 | [7 empty] | 24 | 6582.01 | [5 empty] | 234 | [106 empty] | 24 | 7330 | [5 empty] | 165.8558
|  |  | 25 | 5254 |  | 329 | [7 empty] | 25 | 7142 | [5 empty] | 180.2022 | [106 empty] | 25 | 7479 | [5 empty] | 153.7035
Reset Form

## D-D
5 | Number Of Points To Resolve To
14 | Append To This Reach
BACK TO TOPOGRAPHY PAGE
X (m) | Z (m)
7219 | 168.9697 | 7279 | 163.5207
7279 | 163.5207 | 7329 | 158.5837
7329 | 158.5837 | 7379 | 154.6607
7379 | 154.6607 | 7429 | 151.9714
7429 | 151.9714 | 7429 | 151.9714
GO

## D-C
| MAIN |  |  | FEASIBILITY |  | DESIGN |  | PLANNING |  | IMPLEMENTATION |  | EVALUATION |  |  |  | OPTIONS | HELP
HOME |  | System Design: Add Components | [16 empty] | STORAGE TANK | [5 empty] | Only needed if intake flow rate is
greater then peak demand.
ACTIONS | [18 empty] | Total System |  | 6.3 |  | L/sec |  | STORAGE TANK REQUIRED |  | If needed, Tank
|  | Below is a list of different components to be added to a design of a Gravity Flow Water System. It is important to note that no two components may occupy the same point on the same reach, or be located where a new reach begins! | [16 empty] | Water Intake: | [7 empty] | must be located on
TOPO INFO | [18 empty] | Total System |  | 21.125 |  | L/sec |  |  |  | Reach 1 | 22
[19 empty] | Water Demands: | [7 empty] | At Point:
COMPONETS
GENERATE |  |  | WATER SOURCES | [5 empty] | Add water sours, their |  |  |  | NON-STORAGE TANKS |  |  |  |  | Add tanks that do not offer |  |  |  | PUBLIC TAPSTANDS | [6 empty] | Add public tapstands to |  | PRIVATE TAPSTANDS |  |  | Add private tapstands to |  | CLUSTERS OF TAPSTANDS |  |  |  | Add clusters of private |  | OTHER EXTRACTION POINTS |  |  |  | Add other types of extraction
[9 empty] | location, and flow rates | [8 empty] | water storage: i.e. brake | [10 empty] | the water systems |  |  |  |  | the water system | [5 empty] | tapstands to the water system | [5 empty] | (wash areas, showers, etc.)
REPORT |  |  | Reach | Point | Flow Rate (L/S) |  | Notes / source Name / source type | [5 empty] | Reach | Point |  |  |  | pressure, sedimentation, etc. |  |  |  | Reach |  | Point |  | Notes / Tapstands Name / Tapstands Area |  |  |  |  | Reach | Point | Notes / Tapstands Name / Tapstands Owner |  |  | Reach | Point | Tap | Notes / Tapstands Name / Tapstands type |  |  | Reach | Point | extraction | Notes / Tapstands Name / Tapstands type
|  | # | [8 empty] | # |  |  |  | Notes / Tank Name / Tank Type |  |  |  |  | # | [9 empty] | # |  |  |  |  | # |  |  | count |  |  | # |  |  | rate (L/S)
|  | 1 | 1 | 1 | 6.3 | [5 empty] | 1 |  | 1 | 2 | [20 empty] | 1 | 2 | 5 | 8
[11 empty] | 2 |  | 1 | 9 | [20 empty] | 2 | 2 | 10 | 12
[11 empty] | 3 |  | 6 | 15 | [20 empty] | 3 | 2 | 24 | 7
[11 empty] | 4 |  | 9 | 9 | [20 empty] | 4 | 3 | 3 | 16
[11 empty] | 5 |  | 9 | 18 | [20 empty] | 5 | 4 | 3 | 4
[35 empty] | 6 | 5 | 5 | 6
[35 empty] | 7 | 6 | 4 | 21
[35 empty] | 8 | 6 | 7 | 11
[35 empty] | 9 | 6 | 19 | 7
[35 empty] | 10 | 6 | 24 | 13
[35 empty] | 11 | 7 | 8 | 3
[35 empty] | 12 | 8 | 7 | 2
[35 empty] | 13 | 9 | 14 | 16
[35 empty] | 14 | 9 | 20 | 14
[35 empty] | 15 | 9 | 24 | 2
[35 empty] | 16 | 10 | 2 | 5
[35 empty] | 17 | 11 | 10 | 8
[35 empty] | 18 | 12 | 2 | 5
[35 empty] | 19 | 13 | 3 | 5
[35 empty] | 20 | 14 | 5 | 4
RESET FORM

## D-G
| MAIN |  |  | FEASIBILITY |  | DESIGN |  | PLANNING |  | IMPLEMENTATION |  |  | EVALUATION |  |  | OPTIONS |  |  |  | HELP
HOME |  | System Design: Plan Generation
Optimization Variables
ACTIONS
This module generates a plan for the water system using a simple Genetic Algorithm. The software will select a specific type and diameter for each section of each reach in the system. The user can define a specific type or diameter for the pipes in a section by specifying the desired choice in the two orange columns below. The optimization engine can be controlled by altering the values on the right. A maximum population of 1000, and a maximum count of 10,000 generations is available. The tolerance determines how many generations without a decrease in system cost must pass before the program terminates. The crossover coefficient and mutation coefficient dictate how the population breeds and mutates. 1.) By clicking on the "Generate Base Network" button, the information from the topography information page and the component information page is copied to this sheet. 2.) By Clicking on the "Generate System Design" button, the software looks for a configuration which satisfies the pressure and flow constraints. 3.) By Clicking on the "Generate Report" button, a report is created of the new design. Plots are created of the Ground Surface Profile (GSP) and Hydraulic Grade lines (HGL).
TOPO INFO | [13 empty] | Variable |  |  |  |  | Value
[14 empty] | Population Size |  |  |  |  | 626
COMPONETS
[14 empty] | Generation Number |  |  |  |  | 10000
GENERATE
[14 empty] | Tolerance |  |  | Runs w/ changing |  | 100
REPORT
[14 empty] | Crossover Coef. |  |  |  |  | 0.5
[14 empty] | Mutation Coef. |  |  |  |  | 0.05
Running Optimization . . .
[14 empty] | Run Start: |  |  |  |  | 17:34
Estimated Cost ($$)
[14 empty] | Run End: |  |  |  |  | 17:23
[14 empty] | Run Duration: |  |  |  |  | -0.007338
WATER SYSTEM DESIGN
|  | Point | Distance (m) |  | Elevation (m) |  | Flow Rate (L/S) |  | Suggested |  | User Defined | Suggested |  |  | User Defined |  |  | Head Loss (m) |  | Hydraulic | Residual |  | Static | Notes
[9 empty] | Tube Type (#) |  | Tube Type (#) | Diameter (cm) |  |  | Diameter (#) |  |  |  |  | Grade Line (m) | Head (m) |  | Head (m)
|  |  | 0 |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
|  |  | -- |  | --
Generate Base Network
Generate System Design
Generate Report
Reset Form

## da
DESIGN- | Action Results
Socio - Cultural Respect | TRUE | [12 empty] | Pipe Information
4 | TRUE
| TRUE | [13 empty] | Type Name | PVC PIPE | CE PIPE | enter pipe type | enter pipe type | enter pipe type | enter pipe type |  |  | Name | PVC PIPE | CE PIPE
| TRUE | [13 empty] | Hazen C | 150 | 150 | friction coefficient | friction coefficient | friction coefficient | friction coefficient |  |  | Hazen C | 150 | 150 | 0 | 0 | 0 | 0
Community Participation | TRUE | [13 empty] | Max Head | 300 | 400 | enter maximum head | enter maximum head | enter maximum head | enter maximum head |  |  | Max Head | 300 | 400 | 0 | 0 | 0 | 0
4 | TRUE | [12 empty] | d1 | 25.4 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE |  | d1 | 25.4 | 240.85 | 400 | 0 | 0 | 0 | 0
| TRUE | [12 empty] | d2 | 19.1 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE |  | d2 | 19.1 | 194.61 | 300 | 0 | 0 | 0 | 0
| TRUE | [12 empty] | d3 | 38.1 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE |  | d3 | 38.1 | 429.34 | 500 | 0 | 0 | 0 | 0
Political Cohesion | TRUE | [12 empty] | d4 | 50.8 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE |  | d4 | 50.8 | 560.66 | 700 | 0 | 0 | 0 | 0
4 | TRUE | [12 empty] | d5 | 12.7 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE |  | d5 | 12.7 | 128.2 | 200 | 0 | 0 | 0 | 0
| TRUE | [12 empty] | d6 | 100 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE |  | d6 | 100 | 725.96 | 1000 | 0 | 0 | 0 | 0
| TRUE | [12 empty] | d7 | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE |  | d7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Economic Sustainability | TRUE | [12 empty] | d8 | enter tube diameter | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | d8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TRUE | [12 empty] | d9 | enter tube diameter | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | d9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TRUE | [12 empty] | d10 | enter tube diameter | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | d10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TRUE | [22 empty] | Valid | 1 | 1 | 0 | 0 | 0 | 0
Environmental Sustainability | TRUE | [13 empty] | PublicQ: | 0.125 | [7 empty] | Avg Cst | 9.8885 | 14.0176 | 0 | 0 | 0 | 0
4 | TRUE | [13 empty] | PrivateQ: | 0.125 | [7 empty] | Rank | 5 | 6 | 1 | 1 | 1 | 1
| TRUE | [13 empty] | MinHead | 7 |  |  |  | Percent: | 100% |  |  | DataPts | 6 | 6 | 0 | 0 | 0 | 0
| TRUE | [13 empty] | MaxTap | 56 |  |  |  | Start: | 17:34
20 | [19 empty] | End: | 17:23
| WATER SYSTEM DESIGN | [18 empty] | Runs
Cost:
[20 empty] | Penalty | Running Optimization . . .
| Point | Distance (m) | Elevation (m) | Q | Suggested | User Defined | Suggested | User Defined | Head Loss (m) | Hydraulic | Residual | Static | STORAGE TANK
[5 empty] | Tube Type (#) | Tube Type (#) | Diameter (cm) | Diameter (cm) |  | Grade Line (m) | Head (m) | Head (m) |  | Point | X | Z | Q | TYPE | DIAM | Section Loss | HGL | Residual | Static | Notes
[6 empty] | 0 |  | 0 | [5 empty] | 1 | 0 | 450 | 6.3 | [5 empty] | 0 | S | SOURCE 1
[14 empty] | 2 | 182 | 450 | 6.3 | 1 |  |  |  |  | 0 | E | TANK 1
[6 empty] | 0 |  | 0 | [5 empty] | 3 | 182.01 | 450 | 6.3 | 1 |  |  |  |  | 0 | T | TANK 1
[14 empty] | 4 | 182.01 | 450 | 6.3 | 1 |  |  |  |  | 0
[6 empty] | 0 |  | 0 | [5 empty] | 5 | 833 | 405 | 6.3 | 1 |  |  |  |  | 45
[14 empty] | 6 | 853 | 405 | 6.3 | 1 |  |  |  |  | 45
[6 empty] | 0 |  | 0 | [5 empty] | 7 | 990 | 426 | 6.3 | 1 |  |  |  |  | 24
[14 empty] | 8 | 1130 | 438 | 6.3 | 1 |  |  |  |  | 12
[6 empty] | 0 |  | 0 | [5 empty] | 9 | 1588 | 421 | 6.3 | 1 |  |  |  |  | 29
[14 empty] | 10 | 1996 | 376 | 6.3 | 1 |  |  |  |  | 74 | E | TANK 2
[6 empty] | 0 |  | 0 | [5 empty] | 11 | 1996.01 | 376 | 6.3 | 1 |  |  |  |  | 0 | T | TANK 2
[14 empty] | 12 | 1996.01 | 376 | 6.3 | 1 |  |  |  |  | 0
[6 empty] | 0 |  | 0 | [5 empty] | 13 | 2268 | 316 | 6.3 | 1 |  |  |  |  | 60
[14 empty] | 14 | 2281 | 317 | 6.3 | 1 |  |  |  |  | 59
[6 empty] | 0 |  | 0 | [5 empty] | 15 | 2337 | 334 | 6.3 | 1 |  |  |  |  | 42
[14 empty] | 16 | 2488 | 303 | 6.3 | 1 |  |  |  |  | 73
[6 empty] | 0 |  | 0 | [5 empty] | 17 | 2507 | 303 | 6.3 | 1 |  |  |  |  | 73
[14 empty] | 18 | 2604 | 311 | 6.3 | 1 |  |  |  |  | 65
[6 empty] | 0 |  | 0 | [5 empty] | 19 | 3211 | 290 | 6.3 | 1 |  |  |  |  | 86
[14 empty] | 20 | 3813 | 257 | 6.3 | 1 |  |  |  |  | 119
[6 empty] | 0 |  | 0 | [5 empty] | 21 | 4096 | 243 | 6.3 | 1 |  |  |  |  | 133
[14 empty] | 22 | 4225 | 254 | 6.3 | 1 |  |  |  |  | 122
[6 empty] | 0 |  | 0 | [5 empty] | 23 | 4537 | 281 | 6.3 | 1 |  |  |  |  | 95
[14 empty] | 24 | 4974 | 291 | 6.3 | 1 |  |  |  |  | 85 | E | STORAGE TANK
[6 empty] | 0 |  | 0 | [5 empty] | 25 | 4974.01 | 291 | 21.125 | 1 |  |  |  |  | 0 | T | STORAGE TANK
[14 empty] | 26 | 5132 | 330 | 21.125 | 1 |  |  |  |  | -39
[6 empty] | 0 |  | 0 | [5 empty] | 27 | 5201 | 340 | 21.125 | 1 |  |  |  |  | -49
[14 empty] | 28 | 5254 | 329 | 21.125 | 1 |  |  |  |  | -38
[6 empty] | 0 |  | 0 | [5 empty] | 29 | -28 | 329 | [7 empty] | R | REACH 2
[14 empty] | 30 | 5256 | 328 | 21.125 | 1 |  |  |  |  | -37
[6 empty] | 0 |  | 0 | [5 empty] | 31 | 5258 | 327 | 21.125 | 1 |  |  |  |  | -36
[14 empty] | 32 | 5354 | 316.116 | 21.125 | 1 |  |  |  |  | -25.116
[6 empty] | 0 |  | 0 | [5 empty] | 33 | 5474 | 311.3595 | 21.125 | 1 |  |  |  |  | -20.3595 | E | CLUSTER 1 (8 taps)
[14 empty] | 34 | 5543 | 308.5722 | 20.125 | 1 |  |  |  |  | -17.5722
[6 empty] | 0 |  | 0 | [5 empty] | 35 | 5588 | 305.4991 | 20.125 | 1 |  |  |  |  | -14.4991
[14 empty] | 36 | 5621 | 307.004 | 20.125 | 1 |  |  |  |  | -16.004
[6 empty] | 0 |  | 0 | [5 empty] | 37 | 5673 | 311.216 | 20.125 | 1 |  |  |  |  | -20.216
[14 empty] | 38 | 5818 | 315.7111 | 20.125 | 1 |  |  |  |  | -24.7111 | E | CLUSTER 2 (12 taps)
[6 empty] | 0 |  | 0 | [5 empty] | 39 | 5820 | 318.6195 | 18.625 | 1 |  |  |  |  | -27.6195
[14 empty] | 40 | 5822 | 316.0407 | 18.625 | 1 |  |  |  |  | -25.0407
[6 empty] | 0 |  | 0 | [5 empty] | 41 | 5943 | 310.5 | 18.625 | 1 |  |  |  |  | -19.5
[14 empty] | 42 | 6042 | 301.0336 | 18.625 | 1 |  |  |  |  | -10.0336
[6 empty] | 0 |  | 0 | [5 empty] | 43 | 6142 | 302 | 18.625 | 1 |  |  |  |  | -11
[14 empty] | 44 | 6242 | 283.2413 | 18.625 | 1 |  |  |  |  | 7.7587
[6 empty] | 0 |  | 0 | [5 empty] | 45 | 6279 | 279.5344 | 18.625 | 1 |  |  |  |  | 11.4656
[14 empty] | 46 | 6279.01 | 279.5344 | 18.625 | 1 |  |  |  |  | 11.4656
[6 empty] | 0 |  | 0 | [5 empty] | 47 | 6357 | 269 | 18.625 | 1 |  |  |  |  | 22
[14 empty] | 48 | 6406 | 264.5678 | 18.625 | 1 |  |  |  |  | 26.4322
[6 empty] | 0 |  | 0 | [5 empty] | 49 | 6445 | 256.8 | 18.625 | 1 |  |  |  |  | 34.2
[14 empty] | 50 | 6527 | 241.832 | 18.625 | 1 |  |  |  |  | 49.168
[6 empty] | 0 |  | 0 | [5 empty] | 51 | 6582 | 234 | 18.625 | 1 |  |  |  |  | 57
[14 empty] | 52 | 6582.01 | 234 | 18.625 | 1 |  |  |  |  | 57 | E | CLUSTER 3 (7 taps)
[6 empty] | 0 |  | 0 | [5 empty] | 53 | 7142 | 180.2022 | 17.75 | 1 |  |  |  |  | 110.7978
[14 empty] | 54 | -53 | 180.2022 | [7 empty] | R | REACH 3
[6 empty] | 0 |  | 0 | [5 empty] | 55 | 5489 | 315.5086 | 17.75 | 1 |  |  |  |  | -24.5086
[14 empty] | 56 | 5553 | 311.1688 | 17.75 | 1 |  |  |  |  | -20.1688 | E | CLUSTER 4 (16 taps)
[6 empty] | 0 |  | 0 | [5 empty] | 57 | 5553 | 311.1688 | 15.75 | 1 |  |  |  |  | -20.1688
[14 empty] | 58 | -57 | 311.1688 | [7 empty] | R | REACH 4
[6 empty] | 0 |  | 0 | [5 empty] | 59 | 5870 | 318.6195 | 15.75 | 1 |  |  |  |  | -27.6195
[14 empty] | 60 | 5912 | 324.9483 | 15.75 | 1 |  |  |  |  | -33.9483 | E | CLUSTER 5 (4 taps)
[6 empty] | 0 |  | 0 | [5 empty] | 61 | 5912 | 324.9483 | 15.25 | 1 |  |  |  |  | -33.9483
[14 empty] | 62 | -61 | 324.9483 | [7 empty] | R | REACH 5
[6 empty] | 0 |  | 0 | [5 empty] | 63 | 5841 | 317.6427 | 15.25 | 1 |  |  |  |  | -26.6427
[14 empty] | 64 | 5891 | 308.0308 | 15.25 | 1 |  |  |  |  | -17.0308
[6 empty] | 0 |  | 0 | [5 empty] | 65 | 5941 | 297.7064 | 15.25 | 1 |  |  |  |  | -6.7064
[14 empty] | 66 | 5972 | 291.7028 | 15.25 | 1 |  |  |  |  | -0.7028 | E | CLUSTER 6 (6 taps)
[6 empty] | 0 |  | 0 | [5 empty] | 67 | 5972 | 291.7028 | 14.5 | 1 |  |  |  |  | -0.7028
[14 empty] | 68 | -67 | 291.7028 | [7 empty] | R | REACH 6
[6 empty] | 0 |  | 0 | [5 empty] | 69 | 5350 | 329.5012 | 14.5 | 1 |  |  |  |  | -38.5012
[14 empty] | 70 | 5432 | 325.1878 | 14.5 | 1 |  |  |  |  | -34.1878
[6 empty] | 0 |  | 0 | [5 empty] | 71 | 5500 | 323.5134 | 14.5 | 1 |  |  |  |  | -32.5134 | E | CLUSTER 7 (21 taps)
[14 empty] | 72 | 5576 | 318.325 | 11.875 | 1 |  |  |  |  | -27.325
[6 empty] | 0 |  | 0 | [5 empty] | 73 | 5633 | 308.6 | 11.875 | 1 |  |  |  |  | -17.6
[14 empty] | 74 | 5738 | 296.3518 | 11.875 | 1 |  |  |  |  | -5.3518 | E | CLUSTER 8 (11 taps)
[6 empty] | 0 |  | 0 | [5 empty] | 75 | 5865 | 288.9509 | 10.5 | 1 |  |  |  |  | 2.0491
[14 empty] | 76 | 6001 | 281.1753 | 10.5 | 1 |  |  |  |  | 9.8247
[6 empty] | 0 |  | 0 | [5 empty] | 77 | 6053 | 285.9 | 10.5 | 1 |  |  |  |  | 5.1
[14 empty] | 78 | 6053.01 | 285.9 | 10.5 | 1 |  |  |  |  | 5.1
[6 empty] | 0 |  | 0 | [5 empty] | 79 | 6185 | 246 | 10.5 | 1 |  |  |  |  | 45
[14 empty] | 80 | 6299 | 274 | 10.5 | 1 |  |  |  |  | 17
[6 empty] | 0 |  | 0 | [5 empty] | 81 | 6414 | 269.1337 | 10.5 | 1 |  |  |  |  | 21.8663
[14 empty] | 82 | 6539 | 272.6453 | 10.5 | 1 |  |  |  |  | 18.3547 | E | TANK 3
[6 empty] | 0 |  | 0 | [5 empty] | 83 | 6539.01 | 272.6453 | 10.5 | 1 |  |  |  |  | 0 | T | TANK 3
[14 empty] | 84 | 6655 | 263.6115 | 10.5 | 1 |  |  |  |  | 9.0338
[6 empty] | 0 |  | 0 | [5 empty] | 85 | 6725 | 252.23 | 10.5 | 1 |  |  |  |  | 20.4153
[14 empty] | 86 | 5804 | 239.4453 | 10.5 | 1 |  |  |  |  | 33.2
[6 empty] | 0 |  | 0 | [5 empty] | 87 | 5897 | 255.8913 | 10.5 | 1 |  |  |  |  | 16.754 | E | CLUSTER 9 (7 taps)
[14 empty] | 88 | 6988 | 270.5692 | 9.625 | 1 |  |  |  |  | 2.0761
[6 empty] | 0 |  | 0 | [5 empty] | 89 | 6988 | 270.5692 | 9.625 | 1 |  |  |  |  | 2.0761
[14 empty] | 90 | -89 | 270.5692 | [7 empty] | R | REACH 7
[6 empty] | 0 |  | 0 | [5 empty] | 91 | 5583 | 316.8542 | 9.625 | 1 |  |  |  |  | -44.2089
[14 empty] | 92 | 5613 | 314.9794 | 9.625 | 1 |  |  |  |  | -42.3341 | E | CLUSTER 10 (13 taps)
[6 empty] | 0 |  | 0 | [5 empty] | 93 | 5640 | 315.6469 | 8 | 1 |  |  |  |  | -43.0016
[14 empty] | 94 | 5671 | 315.8273 | 8 | 1 |  |  |  |  | -43.182
[6 empty] | 0 |  | 0 | [5 empty] | 95 | 5717 | 304.5042 | 8 | 1 |  |  |  |  | -31.8589
[14 empty] | 96 | 5749 | 302.5974 | 8 | 1 |  |  |  |  | -29.9521
[6 empty] | 0 |  | 0 | [5 empty] | 97 | 5766 | 298.2453 | 8 | 1 |  |  |  |  | -25.6 | E | CLUSTER 11 (3 taps)
[14 empty] | 98 | 5766 | 298.2453 | 7.625 | 1 |  |  |  |  | -25.6
[6 empty] | 0 |  | 0 | [5 empty] | 99 | -98 | 298.2453 | [7 empty] | R | REACH 8
[14 empty] | 100 | 5760 | 299.9829 | 7.625 | 1 |  |  |  |  | -27.3376
[6 empty] | 0 |  | 0 | [5 empty] | 101 | 5779 | 291.1607 | 7.625 | 1 |  |  |  |  | -18.5154
[14 empty] | 102 | 5798 | 284.7923 | 7.625 | 1 |  |  |  |  | -12.147
[6 empty] | 0 |  | 0 | [5 empty] | 103 | 5822 | 288.3052 | 7.625 | 1 |  |  |  |  | -15.6599
[14 empty] | 104 | 5838 | 289.8387 | 7.625 | 1 |  |  |  |  | -17.1934
[6 empty] | 0 |  | 0 | [5 empty] | 105 | 5866 | 289.5537 | 7.625 | 1 |  |  |  |  | -16.9084 | E | CLUSTER 12 (2 taps)
[14 empty] | 106 | 5866 | 289.5537 | 7.375 | 1 |  |  |  |  | -16.9084
[6 empty] | 0 |  | 0 | [5 empty] | 107 | -106 | 289.5537 | [7 empty] | R | REACH 9
[14 empty] | 108 | 5360 | 326 | 7.375 | 1 |  |  |  |  | -53.3547
[6 empty] | 0 |  | 0 | [5 empty] | 109 | 5432 | 325.1878 | 7.375 | 1 |  |  |  |  | -52.5425
[14 empty] | 110 | 5500 | 323.5134 | 7.375 | 1 |  |  |  |  | -50.8681
[6 empty] | 0 |  | 0 | [5 empty] | 111 | 5576 | 318.325 | 7.375 | 1 |  |  |  |  | -45.6797
[14 empty] | 112 | 5633 | 308.6 | 7.375 | 1 |  |  |  |  | -35.9547
[6 empty] | 0 |  | 0 | [5 empty] | 113 | 5738 | 296.3518 | 7.375 | 1 |  |  |  |  | -23.7065
[14 empty] | 114 | 5861 | 298.2625 | 7.375 | 1 |  |  |  |  | -25.6172
[6 empty] | 0 |  | 0 | [5 empty] | 115 | 5961 | 275.565 | 7.375 | 1 |  |  |  |  | -2.9197 | E | TANK 4
[14 empty] | 116 | 5961.01 | 275.565 | 7.375 | 1 |  |  |  |  | 0 | T | TANK 4
[6 empty] | 0 |  | 0 | [5 empty] | 117 | 5961.01 | 275.565 | 7.375 | 1 |  |  |  |  | 0
[14 empty] | 118 | 6060 | 260.7283 | 7.375 | 1 |  |  |  |  | 14.8367
[6 empty] | 0 |  | 0 | [5 empty] | 119 | 6166 | 261.2772 | 7.375 | 1 |  |  |  |  | 14.2878
[14 empty] | 120 | 6258 | 262.1556 | 7.375 | 1 |  |  |  |  | 13.4094
[6 empty] | 0 |  | 0 | [5 empty] | 121 | 6344 | 251 | 7.375 | 1 |  |  |  |  | 24.565 | E | CLUSTER 13 (16 taps)
[14 empty] | 122 | 6435 | 249.3801 | 5.375 | 1 |  |  |  |  | 26.1849
[6 empty] | 0 |  | 0 | [5 empty] | 123 | 6585 | 248 | 5.375 | 1 |  |  |  |  | 27.565
[14 empty] | 124 | 6685 | 212.0059 | 5.375 | 1 |  |  |  |  | 63.5591
[6 empty] | 0 |  | 0 | [5 empty] | 125 | 6756 | 199.6 | 5.375 | 1 |  |  |  |  | 75.965 | E | TANK 5
[14 empty] | 126 | 6756.01 | 199.6 | 5.375 | 1 |  |  |  |  | 0 | T | TANK 5
[6 empty] | 0 |  | 0 | [5 empty] | 127 | 6756.01 | 199.6 | 5.375 | 1 |  |  |  |  | 0
[14 empty] | 128 | 6835 | 188.7047 | 5.375 | 1 |  |  |  |  | 10.8953 | E | CLUSTER 14 (14 taps)
[6 empty] | 0 |  | 0 | [5 empty] | 129 | 6975 | 179.4703 | 3.625 | 1 |  |  |  |  | 20.1297
[14 empty] | 130 | 7095 | 180.4011 | 3.625 | 1 |  |  |  |  | 19.1989
[6 empty] | 0 |  | 0 | [5 empty] | 131 | 7219 | 168.9597 | 3.625 | 1 |  |  |  |  | 30.6403
[14 empty] | 132 | 7330 | 165.8558 | 3.625 | 1 |  |  |  |  | 33.7442 | E | CLUSTER 15 (2 taps)
[6 empty] | 0 |  | 0 | [5 empty] | 133 | 7479 | 153.7035 | 3.375 | 1 |  |  |  |  | 45.8965
[14 empty] | 134 | -133 | 153.7035 | [7 empty] | R | REACH 10
[6 empty] | 0 |  | 0 | [5 empty] | 135 | 6480 | 247 | 3.375 | 1 |  |  |  |  | -47.4 | E | CLUSTER 16 (5 taps)
[14 empty] | 136 | 6480 | 247 | 2.75 | 1 |  |  |  |  | -47.4
[6 empty] | 0 |  | 0 | [5 empty] | 137 | -136 | 247 | [7 empty] | R | REACH 11
[14 empty] | 138 | 6635 | 226.2129 | 2.75 | 1 |  |  |  |  | -26.6129
[6 empty] | 0 |  | 0 | [5 empty] | 139 | 6662 | 224.0945 | 2.75 | 1 |  |  |  |  | -24.4945
[14 empty] | 140 | 6706 | 222.6869 | 2.75 | 1 |  |  |  |  | -23.0869
[6 empty] | 0 |  | 0 | [5 empty] | 141 | 6751 | 220.5932 | 2.75 | 1 |  |  |  |  | -20.9932
[14 empty] | 142 | 6801 | 222.4109 | 2.75 | 1 |  |  |  |  | -22.8109
[6 empty] | 0 |  | 0 | [5 empty] | 143 | 6851 | 218.9952 | 2.75 | 1 |  |  |  |  | -19.3952
[14 empty] | 144 | 5891 | 211.2486 | 2.75 | 1 |  |  |  |  | -11.6486
[6 empty] | 0 |  | 0 | [5 empty] | 145 | 5938 | 205.5398 | 2.75 | 1 |  |  |  |  | -5.9398
[14 empty] | 146 | 5978 | 200.5124 | 2.75 | 1 |  |  |  |  | -0.9124 | E | CLUSTER 17 (8 taps)
[6 empty] | 0 |  | 0 | [5 empty] | 147 | 5978 | 200.5124 | 1.75 | 1 |  |  |  |  | -0.9124
[14 empty] | 148 | -147 | 200.5124 | [7 empty] | R | REACH 12
[6 empty] | 0 |  | 0 | [5 empty] | 149 | 6784 | 205.3173 | 1.75 | 1 |  |  |  |  | -5.7173 | E | CLUSTER 18 (5 taps)
[14 empty] | 150 | 6784 | 205.3173 | 1.125 | 1 |  |  |  |  | -5.7173
[6 empty] | 0 |  | 0 | [5 empty] | 151 | -150 | 205.3173 | [7 empty] | R | REACH 13
[14 empty] | 152 | 6974 | 218 | 1.125 | 1 |  |  |  |  | -18.4
[6 empty] | 0 |  | 0 | [5 empty] | 153 | 7010 | 210 | 1.125 | 1 |  |  |  |  | -10.4 | E | CLUSTER 19 (5 taps)
[14 empty] | 154 | 7010 | 210 | 0.5 | 1 |  |  |  |  | -10.4
[6 empty] | 0 |  | 0 | [5 empty] | 155 | -154 | 210 | [7 empty] | R | REACH 14
[14 empty] | 156 | 7279 | 163.5207 | 0.5 | 1 |  |  |  |  | 36.0793
[6 empty] | 0 |  | 0 | [5 empty] | 157 | 7329 | 158.5837 | 0.5 | 1 |  |  |  |  | 41.0163
[14 empty] | 158 | 7379 | 154.6607 | 0.5 | 1 |  |  |  |  | 44.9393
[6 empty] | 0 |  | 0 | [5 empty] | 159 | 7429 | 151.9714 | 0.5 | 1 |  |  |  |  | 47.6286 | E | CLUSTER 20 (4 taps)
[14 empty] | 160 | 7429 | 151.9714 | 0 | 1 |  |  |  |  | 47.6286
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0

## D-R
Community Water System (Original) | [7 empty] | BACK
Jacob Marsh
Community Water System (Original) - Sytem Design
Guaranal and Quita Sueno (Original), Alatamira, Puerto Plata
Reach 1
X (m) | GSP (m) | Q (L/sec) | Material | D (mm) | HGL (m) | Head (m) | Notes

## P-H
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Project Planning
ACTIONS
With the creation of a suitable design, the Planning stage can begin. The PLANNING module provides assistance in creation of a projects budgets and materials lists. Creation of budgets and materials lists is important for ensuring that the project can move forward. Budgets can be presented to donor agencies or supervisors to provide transparency. In order to solicit funds for different projects an itemized budget and design are often required. The PLANNING module includes a few different tools to help in creation of these documents. Space is provided to note all the different components involved in the system. Tools are also provided to diagnose locations where air blocks may arise and where washouts should be considered. A list of all materials needed for the project is generated, and this can be taken to vendors to receive price quotes. Finally, a fully itemized budget can be created at the end of this module.
COMPONENTS
MATERIALS
BUDGET
Reset Planning Module

## P-A
| MAIN |  |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION |  | OPTIONS | HELP
HOME |  | Project Planning: Suggested Actions
ACTIONS
|  | Below is a list of different actions to be undertaken to complete the plans for a Gravity Flow Water System. Check the boxes for each action that has been completed and/or understood. | [6 empty] | NOTE: The Titles for each box are links to full descriptions of each table
COMPONENTS
MATERIALS
BUDGET
Socio - Cultural Respect
Understand the traditional structure of community projects.
Consider the seasonality of labor in setting the timeline.
Explore options for increasing gender equity in project roles and capacity building.
Confirm that labor and resource contributions are equitably divided.
Community Participation
Community input is solicited in refining the selected technical design.
Final technical design is approved through a process of community consensus.
Community members are involved in identifying and sequencing tasks that will be incorporated into an action plan.
The community members and development workers approve of the timeline and responsibilities laid out in the action plan.
Political Cohesion
The roles and responsibilities of partner institutions are defined in a detailed action plan.
Agree on financial commitments.
A timeline is drafted that meets the requirements of all institutions involved.
Final project design and action plan are presented to partner institutions and local, regional, and/or national level authorities.
Economic Sustainability
Verify the costs and availability of resources.
Confirm the community contribution for money, materials, equipment, tools, and labor.
Finalize budget based on local costs, available resources, and community contribution.
Develop an action plan for resource procurement.
Environmental Sustainability
The final project design minimizes ecological disturbance, energy use and waste emissions.
The project design uses renewable and/or recyclable local resources.
The action plan considers the seasonality of resources.
Develop an environmental action plan to mitigate impacts during construction.
Reset Form

## P-C
| MAIN |  |  |  | FEASIBILITY |  | DESIGN |  | PLANNING |  | IMPLEMENTATION |  |  | EVALUATION |  |  |  |  | OPTIONS |  |  |  | HELP
HOME |  | Project Planning: Component Materials | [14 empty] | TANK SIZING TOOL
ACTIONS
COMPONENTS |  | Use this page to mark all the different items that will be needed for the water system. If a design has been generated with the previous module, the pipe configuration can be copied to this module. | [14 empty] | AIR BLOCK / WASHOUT LOCATOR
MATERIALS
BUDGET
|  |  | Pipe Information | [10 empty] | Other Components:
[10 empty] | Individual |  |  | Total Piping
|  |  | Pipe Information can be copied from a design report | [6 empty] | Pipe Length (m): |  |  | Cost | 1 | Enter Component Name Here | [8 empty] | Quantity |  | 2 |  | Enter Component Name Here | [7 empty] | Quantity |  | 3 |  | Enter Component Name Here |  |  |  |  | Quantity |  | 4 | Enter Component Name Here |  | Quantity | 5 | Enter Component Name Here |  | Quantity | 6 | Enter Component Name Here |  | Quantity | 7 | Enter Component Name Here |  | Quantity | 8 | Enter Component Name Here |  | Quantity | 9 | Enter Component Name Here |  | Quantity | 10 | Enter Component Name Here |  | Quantity | 11 | Enter Component Name Here |  | Quantity | 12 | Enter Component Name Here |  | Quantity | 13 | Enter Component Name Here |  | Quantity | 14 | Enter Component Name Here |  | Quantity | 15 | Enter Component Name Here |  | Quantity | 16 | Enter Component Name Here |  | Quantity | 17 | Enter Component Name Here |  | Quantity | 18 | Enter Component Name Here |  | Quantity | 19 | Enter Component Name Here |  | Quantity | 20 | Enter Component Name Here |  | Quantity | 21 | Enter Component Name Here |  | Quantity | 22 | Enter Component Name Here |  | Quantity | 23 | Enter Component Name Here |  | Quantity | 24 | Enter Component Name Here |  | Quantity | 25 | Enter Component Name Here |  | Quantity | 26 | Enter Component Name Here |  | Quantity | 27 | Enter Component Name Here |  | Quantity | 28 | Enter Component Name Here |  | Quantity | 29 | Enter Component Name Here |  | Quantity | 30 | Enter Component Name Here |  | Quantity | 31 | Enter Component Name Here |  | Quantity | 32 | Enter Component Name Here |  | Quantity | 33 | Enter Component Name Here |  | Quantity | 34 | Enter Component Name Here |  | Quantity | 35 | Enter Component Name Here |  | Quantity | 36 | Enter Component Name Here |  | Quantity | 37 | Enter Component Name Here |  | Quantity | 38 | Enter Component Name Here |  | Quantity | 39 | Enter Component Name Here |  | Quantity | 40 | Enter Component Name Here |  | Quantity | 41 | Enter Component Name Here |  | Quantity | 42 | Enter Component Name Here |  | Quantity | 43 | Enter Component Name Here |  | Quantity | 44 | Enter Component Name Here |  | Quantity | 45 | Enter Component Name Here |  | Quantity | 46 | Enter Component Name Here |  | Quantity | 47 | Enter Component Name Here |  | Quantity | 48 | Enter Component Name Here |  | Quantity | 49 | Enter Component Name Here |  | Quantity | 50 | Enter Component Name Here |  | Quantity
|  |  | from the previous module, or entered manually | [6 empty] | 5.78 |  |  | 0
|  |  | D (cm) | Type |  | Meters |  | $ / meter |  | Pipe Count |  | Total Cost |  | Item Name | [6 empty] | Size / Code |  |  | Item Count |  | Item Name | [6 empty] | Size / Code |  |  | Item Count |  | Item Name |  |  |  |  | Size / Code |  | Item Count |  | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count | Item Name |  | Size / Code | Item Count
[14 empty] | Time | [5 empty] | Percent Of Daily Water Usage for time period |  |  |  |  | Tank Flow (L/s) |  |  |  |  | 0.95 | Public Taps: |  |  |  |  | Suggested Tank Volume: |  |  |  |  | 11220
[25 empty] | Safety Factor |  |  |  |  | 1.5 | Private Taps: |  |  |  | 160
[25 empty] | Water Supplied | [5 empty] | Water Demanded |  |  |  |  | Cumulative Deficit |  |  |  |  | Tank Level
[14 empty] | 0:00 to 3:00 am | [5 empty] | 0% |  |  |  |  | 10260 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 11220 |  |  | 11220
[14 empty] | 3:00 to 6:00 am | [5 empty] | 40% |  |  |  |  | 10260 | [5 empty] | 16000 |  |  |  |  | -5740 |  |  |  |  | 5480 |  |  | 5480
[14 empty] | 6:00 to 9:00 am | [5 empty] | 30% |  |  |  |  | 10260 | [5 empty] | 12000 |  |  |  |  | -7480 |  |  |  |  | 3740 |  |  | 3740
[14 empty] | 9:00 to 12:00 am | [5 empty] | 0% |  |  |  |  | 10260 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 11220 |  |  | 11220
[14 empty] | 0:00 to 3:00 pm | [5 empty] | 0% |  |  |  |  | 10260 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 11220 |  |  | 11220
[14 empty] | 3:00 to 6:00 pm | [5 empty] | 0% |  |  |  |  | 10260 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 11220 |  |  | 11220
[14 empty] | 6:00 to 9:00 pm | [5 empty] | 30% |  |  |  |  | 10260 | [5 empty] | 12000 |  |  |  |  | -1740 |  |  |  |  | 9480 |  |  | 9480
[14 empty] | 9:00 to 12:00 pm | [5 empty] | 0% |  |  |  |  | 10260 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 11220 |  |  | 11220
[14 empty] | Total: | [7 empty] | 100% | Total: |  |  |  | 82080 |  | Total: |  |  | 40000 |  | Max Deficit: |  |  | 7480 |  | Daily Surplus: |  |  | 42080 |  |  |  | 74800
Air Block / Washout Possibilities
[14 empty] | Reach |  | Point |  | Issue
Copy Design Pipe Configuration
Reset Form

## P-M
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Project Planning: Materials List
ACTIONS
Text, text, text…..
COMPONENTS
MATERIALS
BUDGET
Project Materials List
|  | Item Name | [7 empty] | Size / Code | Quantity | Price
Set Materials
Create Budget
Reset Form

## P-R
BACK

## I-H
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Project Implementation
ACTIONS
Implementation of water supply projects is the time when physical construction of the proposed system takes place. As noted by Lothe and Phillips, proper planning of how a construction project is to be accomplished is very important in developing nations. Both monetary and time savings can be accrued by appropriate organization of materials and labor for the project. Transportation of materials to the work site can constitute significant challenges for the project supervisor. Lack of materials can slow down construction, and put the project off schedule. Issues with supply of materials can often result in excess costs incurred when managers are forced to purchase materials from vendors which have higher costs then the vendor where the product was originally priced. Labor can be difficult to organize and move to the construction site. The importance of trained labors cannot be understated. Every effort must be made to insure that laborers will be knowledgeable of what their responsibilities are and when and where they must be each day. Creation of a project schedule can help with planning how the construction phase will progress (Mihelcic, Myre, Fry, and Barkdoll 2008).
SCHEDULE
REPORT

## I-A
| MAIN |  |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION |  | OPTIONS | HELP
HOME |  | Project Implementation: Suggested Actions
ACTIONS
|  | Below is a list of different actions to be undertaken in order to implement the water sysem project. Check the boxes for each action that has been completed and/or understood. | [6 empty] | NOTE: The Titles for each box are links to full descriptions of each table
SCHEDULE
REPORT
Socio - Cultural Respect
Set a realistic work schedule, based on available resources and preferred work styles.
Scheduling includes float time to allow for unexpected.
Scheduling includes float time to allow for unexpected.
Use public gatherings to review benefits of the project, promote education, and discuss operation and maintenance.
Community Participation
Involve the community in revisions of the action plan, program changes, and problem solving.
Work with a local foreman or work supervisor in organizing labor.
Train local laborers in any new techniques and tools that are introduced.
Finalize the management plan with respect to the “built” system.
Political Cohesion
Contact institutions in the area for assistance in training and labor requirements.
Inform partner institutions of the start of construction, project milestones and major changes.
Invite local government and NGO officials to view the construction site.
Discuss partner roles in operation and maintenance.
Economic Sustainability
Community members contribute to project implementation.
Recheck the quality of materials and equipment during resource procurement.
Monitor spending and budget restrictions throughout the project implementation phase.
Draft final report on the budget and share with community members and partner organizations.
Environmental Sustainability
Recheck physical and environmental constraints used in the project design and make design corrections if necessary.
Take precautions to avoid contaminating existing water resources and minimize environmental impacts during implementation.
Involve the community in waste management and environmental education.
Restore any areas disturbed during construction.
Reset Form

## I-S
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION |  | EVALUATION | OPTIONS |  | HELP
HOME |  | Project Implementation: Schedule
ACTIONS
Enter the starting and ending dates for each part of the project. The software will then generate a calendar from this information
SCHEDULE
REPORT
|  | Project Scheduling Table | [7 empty] | 2026-07-29
|  | Project Component or Task |  |  | Start Date |  | End Date
Copy Components
Create Project Calendar

## E-H
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Final Evaluation
ACTIONS
The final module of GOODwater provides project supervisors with an evaluation of how sustainably the water supply project was managed. Evaluation is an important stage during mistakes made can be corrected for future projects. This section includes a set of actions and the final report. This report is summary of all the previous modules sustainability scores.

## E-A
| MAIN |  |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION |  | OPTIONS | HELP
HOME |  | Final Evaluation: Suggested Actions
ACTIONS
|  | Below is a list of different actions to be undertaken to complete a final evaluation of the project. Check the boxes for each action that has been completed and/or understood. | [6 empty] | NOTE: The Titles for each box are links to full descriptions of each table
Socio - Cultural Respect
Discuss unanticipated constraints to system use.
Discuss unexpected limitations to maintenance schemes.
Reassess how gender roles affect the proper use and perceived benefits of the system.
Ensure that costs and benefits are equitably distributed within the community.
Community Participation
Community members are actively involved in performing the necessary operation and maintenance.
Conduct a participatory evaluation to get community feedback and suggestions for improvements.
A community organization exists with the capacity to make decisions regarding the operations and maintenance of the system.
The system is controlled by culturally appropriate and traditionally respected people.
Political Cohesion
Invite officials to the opening ceremony.
Coordinating institutions sign a formal agreement that defines their roles and expectations in operation and maintenance of the system.
A locally based institution is involved in project monitoring.
Share monitoring reports and project evaluations with partner institutions.
Economic Sustainability
Estimate realistic, long-term operation and maintenance costs based on the “built” system.
Financing exists to cover projected operation and maintenance costs.
A financial management organization exists to manage operational/maintenance costs and the distribution of benefits.
Regularly review and adjust the financing system.
Environmental Sustainability
Minimize, treat, and dispose of waste properly.
Explore alternative plans for reducing the use of consumables.
Monitor and evaluate environmental impacts.
Continue environmental and hygiene education efforts.
Reset Form
FINAL EVALUATION

## E-R
Jacob Marsh | [7 empty] | BACK
Exeter University
Community Water System (Original) - Final Evaluaiton
Guaranal and Quita Sueno (Original), Alatamira, Puerto Plata
| Total Project Sustainability Score: | 44
Stage Sustainability Report |  | Site Assessment | Project Design | Budgeting | Implementation | Evaluation | Total
| Socio - Cultural Respect | 4 | 4 | 0 | 0 | 4 | 12
| Community Participation | 4 | 4 | 0 | 0 | 0 | 8
| Political Cohesion | 4 | 4 | 0 | 0 | 0 | 8
| Economic Sustainability | 4 | 4 | 0 | 0 | 0 | 8
| Environmental Sustainability | 4 | 4 | 0 | 0 | 0 | 8
| Total: | 20 | 20 | 0 | 0 | 4 | 44

## O-H
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Options
GLOBALS
GOODwater includes three different options pages. These pages can be configured by an institution to unique local conditions and standards. Once these are set many different projects can be worked through without changing these pages. Included here are a set of global variables used throughout the program, GLOBALS; a macro to establish the constants used to estimate the financial estimates in the site assessment modules, FA CONST.; and PIPE INFO, which contains information about types and costs of pipes available in the area.
FA CONST.
PIPE INFO
RESET OPTIONS

## O-GC
| MAIN |  | FEASIBILITY |  | DESIGN | PLANNING |  | IMPLEMENTATION |  | EVALUATION |  | OPTIONS |  | HELP
HOME |  | Options: Information Needed for Feasibility Assessment
GLOBALS
Fill in the blue tables as best able from regional data. At least three different communities are required to calculate some of the constants. When the table is full click on the "RUN" button at right.
FA CONST.
PIPE INFO
|  | Community Data |  | Community Population Size (#) |  |  | System Type (Public or Private) |  | Distance to Water Source (m) |  | Distribution Network Length (m) |  | Elevation of Water Sauce (m) |  | Elevation at Highest Point in Community (m) |  | Elevation at Lowest Point in Community (m)
Community Name
|  | Initial Cost Data |  | Initial Cost of Water Intakes ($$) |  |  | Initial Cost of Main Line to Water Sauce ($$) |  | Initial Cost of Water Storage Tank ($$) |  | Initial Cost Distribution Network ($$) |  |  |  | Cost Assessment Coefficients
[15 empty] | α1 | 59338.6624 | α11 | 0.019305
[15 empty] | α2 | 88.3417 | α12 | 0.019305
[15 empty] | α3 | 33.37 | β1 | 0.24485
[15 empty] | α4 | 33.37 | β2 | 0.20432
[15 empty] | α5 | 0.00047046 | β3 | 0
[15 empty] | α6 | 8.4658e-07 | β4 | 3.1884
[15 empty] | α7 | 90000 | β5 | 0.0017192
[15 empty] | α8 | 0.00094253 | β6 | 0.64108
[15 empty] | α9 | 4.3853 | β7 | 0
[15 empty] | α10 | 4.4308
|  | Operating Costs |  | Operational Cost of Water Intakes ($$) |  |  | Operational Cost of Main Line ($$) |  | Operational Cost of Water Tank ($$) |  | Operational Cost of Distribution ($$)
Fill in the blue tables as best able from regional data. Cost Values can of be any type of Currency. Note, if only relative elevations are known, enter these as positive and negative values and leave the "Highest Point in Community" column blank. If estimates of both public and private systems are desired data must be entered for both types of systems
RUN
RESET FORM

## O-GV
| MAIN |  | FEASIBILITY | DESIGN | PLANNING |  | IMPLEMENTATION |  | EVALUATION |  |  | OPTIONS | HELP
HOME |  | Options: Global variables
GLOBALS
Fill in the blue tables as best able from regional data. Suggested values are presented below. The form can be reset with the button at the right.
FA CONST.
PIPE INFO
|  | Global Variables |  |  |  | Value |  | Units |  | Suggested value
Variable Name
|  | Tapstands Water Allotment (PUBLIC) |  |  |  | 50 |  | L/person/Day |  | 50 | (Howard 2003)
|  | Tapstands Water Allotment (PRIVATE) |  |  |  | 50 |  | L/person/Day |  | 100 | (Howard 2003)
|  | Number of Users Per Tapstands (PUBLIC) |  |  |  | 250 |  | persons |  | 250 | (Reed 2005)
|  | Number of Users Per Tapstands (PRIVATE) |  |  |  | 5 |  | persons |  | 5
|  | Minimum Flow rate per Tapstands (PUBLIC) |  |  |  | 0.125 |  | L/sec |  | 0.125 | (Reed 2005)
|  | Minimum Flow rate per Tapstands (PRIVATE) |  |  |  | 0.125 |  | L/sec |  | 0.125 | (Reed 2005)
|  | Ordinary Soil Excavation |  |  |  | 0.55 |  | Laborer-days/m^3 |  | 0.55 | (Jordan 1984)
|  | Gravelly Soil Excavation |  |  |  | 0.77 |  | Laborer-days/m^3 |  | 0.77 | (Jordan 1984)
|  | Boulder Mix Excavation |  |  |  | 1.1 |  | Laborer-days/m^3 |  | 1.1 | (Jordan 1984)
|  | Medium Rock Cutting |  |  |  | 1.6 |  | Laborer-days/m^3 |  | 1.6 | (Jordan 1984)
|  | Hard Rock Cutting |  |  |  | 2.5 |  | Laborer-days/m^3 |  | 2.5 | (Jordan 1984)
|  | Pipe Trench Depth |  |  |  | 1 |  | m |  | 1 | (Jordan 1984)
|  | Trench Width |  |  |  | 0.4 |  | m |  | 0.4 | (Jordan 1984)
|  | Minimum Head Throughout Network |  |  |  | 7 |  | m |  | 7 | (Jordan 1984)
|  | Maximum Head At Tapstands and Tanks |  |  |  | 56 |  | m |  | 56 | (Jordan 1984)
RESET FORM

## O-P
| MAIN |  | FEASIBILITY |  | DESIGN |  |  | PLANNING |  | IMPLEMENTATION |  | EVALUATION |  |  | OPTIONS |  | HELP
HOME |  | Options: Pipe Information
GLOBALS
Enter cost values for each type of pipe. Costs are in $ per meter.
FA CONST.
PIPE INFO
[6 empty] | Diameter Number | Type Number: |  |  | 1 | 2 |  |  | 3 |  | 4 |  | 5 | 6
[7 empty] | Pipe Type: |  |  | PVC PIPE | CE PIPE |  |  | enter pipe type |  | enter pipe type |  | enter pipe type | enter pipe type
[7 empty] | Hazen Williams C : |  |  | 150 | 150 |  |  | friction coefficient |  | friction coefficient |  | friction coefficient | friction coefficient
[7 empty] | Maximun Head (m): |  |  | 300 | 400 |  |  | enter maximum head |  | enter maximum head |  | enter maximum head | enter maximum head
|  |  |  | Pipe Diameters (mm) |  | 1 | 25.4 |  |  | 240.85 | 400 |  |  | 0 |  | 0 |  | 0 | 0
[6 empty] | 2 | 19.1 |  |  | 194.61 | 300 |  |  | 0 |  | 0 |  | 0 | 0
[6 empty] | 3 | 38.1 |  |  | 429.34 | 500 |  |  | 0 |  | 0 |  | 0 | 0
[6 empty] | 4 | 50.8 |  |  | 560.66 | 700 |  |  | 0 |  | 0 |  | 0 | 0
[6 empty] | 5 | 12.7 |  |  | 128.2 | 200 |  |  | 0 |  | 0 |  | 0 | 0
[6 empty] | 6 | 100 |  |  | 725.96 | 1000 |  |  | 0 |  | 0 |  | 0 | 0
[6 empty] | 7 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 | 0
[6 empty] | 8 | enter tube diameter |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0
[6 empty] | 9 | enter tube diameter |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0
[6 empty] | 10 | enter tube diameter |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0
Standard Values for common materials
|  |  |  | Material |  |  |  |  | Hazen-Williams C |  |  |  | Suggested Head Limit (m)
|  |  |  | PVC (Class B) |  |  |  |  | 150 |  |  |  | 61
|  |  |  | PVC (Class C) |  |  |  |  | 150 |  |  |  | 91
|  |  |  | PVC (Class D) |  |  |  |  | 150 |  |  |  | 122
|  |  |  | PVC (Class E) |  |  |  |  | 150 |  |  |  | 125
|  |  |  | PE (Medium Density) |  |  |  |  | 150 |  |  |  | 127
|  |  |  | PE (High Density) |  |  |  |  | 150 |  |  |  | 163
|  |  |  | Iron Tubing |  |  |  |  | 120 |  |  |  | 407
|  |  |  | Prestressed Concrete |  |  |  |  | 120 |  |  |  | 204
Clear Form

## H-H
| MAIN |  | FEASIBILITY | DESIGN | PLANNING |  | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Help
ACTIONS
The work described within this document was completed between the years 2004 and 2008. During that time the author was a graduate student of Michigan Technological University (MTU) (Houghton, Michigan), as well as a United States Peace Corps Volunteer serving in the Dominican Republic. The Peace Corps is an international development agency of the United States government which places trained professionals throughout the developing world in order to provide technical assistance to communities and organizations. Michigan Technological University's cooperation with the Peace Corps stems in part from the university's Civil and Environmental Engineering department's Master's International Program (MIP). This program engages students in one year of graduate studies at the university, and assists in placement with the Peace Corps in engineering positions in developing countries worldwide. Students of the program have worked in water supply and treatment, wastewater treatment, water resources management, solid waste management, and other technical fields throughout the world (Mihelcic 2004). One of the stated goals of the MTU-MIP involves incorporating environmental, social, and economic issues into engineering projects through a sustainable framework. Presenting students with extensive overseas field work during their education provides an opportunity for students to learn through experience. The program also generates new research which directly addresses concerns of developing nations (Mihelcic, Phillips, and David W. Watkins 2006). As a member of the MTU-MI program, the author was assigned by the Peace Corps to work as a water and sanitation engineer in the Dominican Republic. Located in the western Caribbean, the Dominican Republic shares the island of Hispaniola with Haiti. With a GDP per capita of $US 3,877 in 2006, and an estimated 9.2 million inhabitants, the Dominican Republic is a developing nation in which the Peace Corps has maintained a presence since 1962. In 2002, an estimated 19 percent of the population, around 1,748,000 Dominicans, lacked access to an improved water source (Economist Intelligence Unit 2007). In this context the author began working in the communities of Guaranal and Quita Sueño, near the town of Altamira, in the north of the country. Working with local leaders and a community water board, a gravity flow water system bringing water to over 150 homes was constructed between 2005 and 2007. For the second half of 2007 the author also served as a technical coordinator for Peace Corps water and sanitation efforts in the Dominican Republic. This role entailed, diagnosing problems, providing advice, and assessing the feasibility of different water project throughout the country. During the lifespan of the water project in the Dominican Republic the author served many different roles. Acting as engineer, foreman, accountant, health trainer, and community organizer for the project, the author became well-informed about many dissimilar aspects of water system implementation, management and operations. Through this work the author became conscious of a lack of tools designed to assist managers of rural water projects. During his time in the Dominican Republic, the author searched for, combined, and created various tools to assists in different stages of the Guaranal and Quita Sueño water system. Upon return to the United States further research into the tools and methodology of rural gravity fed water systems was conducted. This program is a refinement of those investigations.
INPUTS
SOURCES
GOODwater Version 1.0 Released on Feb 21th, 2008

## H-AD
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Help: Actions Summary (Adapted From McConville 2006)
ACTIONS
□ Generate a yearly calendar of work and social life in the community.
INPUTS | • How is a year defined?
• How are the seasons identified?
SOURCES | • What are the characteristics of each season?
• What is the primary employment in the area?
• Is this work constant throughout the year or seasonal?
• What time of year is the busiest? Are other seasons very slow?
• Are there patterns of seasonal migration?
• What is the primary religion in the area?
• When are the major holidays?
• When do weddings, baptisms, and other social ceremonies take place?
BACK | □ Identify social preferences and traditional beliefs associated with water supply and sanitation practices.
• Are certain water sources preferred over others?
• Is there folklore or old stories associated with water sources or water use?
• Are there traditional methods for protection a water source?
• Do people add things to their water? At the source or at home?
• Do people consider sanitation issues around the water sources?
• Are there social caste issues about the use of water from certain sources?
• Is there a history of filtering or screening water sources?
• Are there seasonal changes in the quality of the water supply? How are they explained?
• What is the preferred sanitation method in the community?
• What are preferred methods of anal cleansing?
• How do people feel about handling excreta (even when decomposed)?
• Are the religious constraints to be considered?
• Do people believe that excreta are harmful? .
• Are people afraid to use latrines? Why?
• Are there taboos associated with washing hands with soap? (In Mali, this practice was believed to wash away a person’s wealth)
• For further examples refer to Pickford, 1995.
BACK | □ Determine the level of health education in the community.
• Have community members been involved in answering questions on community health? In formal and informal settings?
• What is their education background?
• What health education issues are covered in schools?
• Who receives education? Men or women? (Note: that there may be discrepancies between who receives education and who performs water/sanitation related tasks)
• How often do people get sick in the community?
• Why do people get sick? (According to them)
• Do people connect water and sanitation issues with disease?
• What is the community motivation for improved water and sanitation services?
• Are there health care facilities available?
• How is the quality of the water? How is quality perceived in the community?
• How do you perceive the cleanliness of the community? How do community members perceive it?
• Do they wash their hands with soap?
• Do they have a latrine?
• Do they use a latrine? Do the children?
BACK | □ Recognize differences in gender roles in water and sanitation.
• How do men use water? How much?
• How do women use water? How much?
• Who provides water for the household? Agriculture? Business?
• How much time do men/women spend per day on water collection?
• Do men and women follow separate sanitation practices?
• Are there separate latrines for men and women?
• Who is in charge of the children’s hygiene?
BACK | □ Conduct a participatory needs assessment at the local level to determine local development priorities.
• Did you use a participatory approach to needs assessment? There are a range of methodologies based on a participatory approach to evaluate development needs, for example: Rapid Rural Appraisal (RRA), Participatory Rural Appraisal (PRA), and Participatory Analysis for Community Action (PACA). In general, they all aim to identify community problems and to plan solutions with the active participation of the community members (Selener et al., 1999). Each method uses a set of “tools” to assist the locals in analyzing the characteristics of their community (community map, social calendars), identifying problems (problem lists, priority analysis), and developing possible solutions (solution brainstorming, feasibility matrix). Participatory tools are most useful when a representative group of community members are involved (men, women, youth, elders, ethnic groups, community leaders and organizations). The participatory needs assessment must take place in the community itself. In depth literature can be found on all of these methods. It is not necessary that all techniques be used during the needs assessment. In fact, development workers should select the tools that are the most applicable to the community. Whatever tools are used the result should still be the identification of the top community needs.
• Is the group involved in the needs assessment representative? Are they influenced by local power groups?
• Can the following types of questions be answered by community members?
􀂃 What are the general characteristics of this community? (employment, services available, ethnic groups, community history)
􀂃 What are the strengths of the community?
􀂃 What are the problems in the community?
􀂃 What is the present level of satisfaction with the existing water/sanitation system?
􀂃 What are the causes and effects of these problems?
􀂃 Which problems have priority for the community?
􀂃 What can be done to address the problems?
􀂃 Does the community have knowledge of options for improved water/sanitation systems?
􀂃 What are the preferred options?
􀂃 What technical, financial, and capacity building assistance does the community need to reach these solutions?
BACK | □ Identify stakeholders and community leaders.
• Who will be directly affected by project intervention?
• Who will be indirectly affected?
• Who will pay?
• Are both genders considered?
• Are all age groups considered?
• Are there ethnic groups with varying needs? Can they be equally or proportional represented in the project process?
• Who are the community leaders?
• Who are the local influential people (LIPs)?
• Are there people with veto power? (mayor, village chef)
• Are there influential people without official titles who will affect how others accept the project? (leading scorer on the soccer team, favorite old man, people of wealth or connections)
• Are all these people behind the project? What will make them agree?
• Are there any existing water/sanitation committees?
BACK | □ Determine the type of political organization and cohesion at the community level.
• How is the community governed?
• Who are the decision makers in the community? Official? Unofficially?
• How representative is the community government?
• What is the level of participation in community decision making?
• Who implements the decisions?
• What are the rules and procedures governing community action?
• What is the level of participation in community activities?
BACK | □ Reach a consensus with community members that project intervention is appropriate.
• Is there a perceived need for water and/or sanitation intervention within the community?
• Do community members understand the project possibilities?
• Is the community aware of the capabilities/limitations of the development workers?
• Are community priorities in line with development workers’ area of expertise?
• Is there agreement within the community to participate in project intervention?
BACK | □ Conduct a situational analysis of regional and national issues such as political structure and stability, government policies, and foreign aid.
• Are there any overwhelming local/regional issues that may affect the project?
􀂃 War
􀂃 Drought
􀂃 Disease (AIDS and other epidemics)
• How stable is the national government?
• What is the financial situation of the country?
􀂃 Debt levels
􀂃 Inflation rates
• What is the structure of the national government?
• What do community members think about the government?
• How active are government officials in the community?
• Does the government address water and sanitation issues?
• Are there government programs/initiatives in water/sanitation?
• How transparent are government finances and policies?
• How prominent are foreign aid projects?
• Are there NGO programs/initiatives in water/sanitation in the area?
• Have you looked at potential information sources such as: UNDP Human Development Report, local interviews, government and NGO reports?
BACK | □ Ensure that proposed project is consistent with regionally identified development priorities and plans.
• What are the priorities outlined in the National Poverty Reduction Strategy Papers (PSRPs), National Strategic Plans, and/or Sector-Wide Approaches (Swaps)? These are national initiatives that outline the development priorities for the country. There will be more government funding and institutional support for projects that address these priorities.
• Are there local development schedules within the community or region? (check with mayor, village counsel, community leaders)
• What is the availability of grants or aid money for water and/or sanitation intervention?
BACK | □ Research the history of NGO and government projects in the area.
• What NGOs have worked in the community before?
• What type of project were they involved in?
• Were they successful?
• What work has the government done in the area?
• How was the community involved in the project implementation?
• Are past project reports available?
• Are the projects on-going?
BACK | □ Establish communication lines with existing NGO and/or government institutions in the area.
• Have government officials in the area been contacted?
• Have NGOs with a history in the area been contacted?
• Are they familiar with your organization?
• What initiatives/projects are they currently working on in the area?
• What advice do they have for working in the area?
BACK | □ Understand the local and national economic situation (poverty level, employment, cost of living, flow of resources).
• What is the primary source of employment?
􀂃 National?
􀂃 Locally?
• How stable is the employment level?
• What is the average income?
• How is wealth distributed? (ratios of high/low income, inequality in wealth)
• What is the average cost of living in the community?
• What do people spend money on? When?
• Do people rent or own their property?
• What are indicators of wealth? (livestock, vehicle, improved home, multiple wives)
BACK | □ Understand how the community economic situation is affected by water and sanitation issues.
• Is income lost due to disease?
• How do people compensate for the loss of children?
• How much time is spent gathering water or dealing with sanitation?
• What percentage of income is spent on water and/or sanitation services?
• Do community members understand the economic consequences of water and sanitation systems?
• Would improved services provide economic gains?
BACK | □ Identify sources of monetary and non-monetary resources (materials, labor, and tools) within the community.
• How do people make money?
􀂃 Paid salary
􀂃 Agriculture
􀂃 Trade
􀂃 Small enterprises (hand crafts, food sales at market, odd jobs)
• How constant is the income?
􀂃 Does it vary by season?
􀂃 Can people save money?
• Does this vary by gender?
• Are there construction tools (wheelbarrows, shovels, picks, masonry tools) available?
• Is aggregate (sand, gravel, or rock) or lumber available?
• Can a community labor force be organized?
• Does the community have the means to transport supplies?
BACK | □ Assess the community willingness-to-pay in both monetary and non-monetary terms for current water and sanitation services.
• What do people pay for water and sanitation services?
􀂃 In cash
􀂃 In organized community labor
􀂃 In materials
• If there are fees (monetary or otherwise) for current services do community members pay them?
• Are current services considered adequate?
• Would people be willing to pay for an improved water supply or sanitation services?
• Do people rent or own their property?
􀂃 It can affect how much they are willing to pay for improvements to the property
􀂃 Will landlords charge higher rent if water/sanitation services are improved?
􀂃 Are tenants willing to pay higher rent for improved services?
BACK | □ Identify local resources for water and sanitation.
• What is the present system for water supply?
• What are potential water sources in the area?
􀂃 How reliable are they?
􀂃 What quantity and quality of water can they produce?
􀂃 Where are they located?
• What systems are present for sanitation (excreta, grey water, and refuse disposal)?
􀂃 How many people are served?
􀂃 Are the systems well used?
• Where is water used? And reused?
• How do water or sanitation needs compare to the supply?
BACK | □ Collect data on climate and environmental constraints that will factor into project design.
• Did you consider the following set of data?
􀂃 Soil conditions
􀂃 Groundwater levels
􀂃 Topography
􀂃 Physical size of village
􀂃 Population trends
􀂃 Seasonal climate variations (Rainfall, Temperature ranges)
􀂃 Stream and river flow rates
􀂃 Evaporation and run-off data
• Can community members assist in the collection of this data?
BACK | □ Identify potential environmental concerns at the local and regional level.
• Are any of the following current environmental concerns? Is there potential that they will become issues?
􀂃 Desertification
􀂃 Deforestation
􀂃 Erosion
􀂃 Overgrazing
􀂃 Soil salination
􀂃 Aquifer depletion
􀂃 Ecosystem/watershed deterioration
􀂃 Loss of biodiversity
• How severe are the impacts?
BACK | □ Determine community understanding of environmental problems and the willingness to correct them.
• How does the community perceive the threats to the environment?
• Can they identify potential environmental concerns?
• Are they concerned about ecosystem loss or climate change?
• What they received education concerning environmental problems?
• Would they be willing to change their behavior patterns for environmental benefits?
Design Stage
BACK | □ Assess how the proposed interventions will affect daily activities and socio-cultural roles within the community.
• Can you brainstorm potential social advantages and disadvantages of potential systems?
• Will the new system elevate or lower the social status of any group or individual? (By giving them new responsibilities or eliminating their roles?)
• Does the new system have the potential to shift social values? Is this positive or negative?
• How can designs address these concerns so that the system will be culturally acceptable?
Will the system result in increased or decreased free time? For whom?
􀂃 Water supply systems can reduce the amount of time spent transporting water to households.
􀂃 Yet, hand pumps installed on borehole wells in Mali often yielded less water per hour than the women could pull by hand from hand-dug wells.
􀂃 Improved sanitation systems may be more convenient, but will they require increase time for cleaning and structure maintenance.
• How will these changes in free time affect the lives of community members?
􀂃 Will increased free time allow for gainful economic employment?
􀂃 Will it affect social time? (Women often socialize together at the water source)
􀂃 Will it affect how children are employed in household chores? (If children no longer fetch water, what will they do? Is it reasonable to expect that they will be able to go to school?)
• Will the new system affect political or power roles in the community?
BACK | □ Evaluate the willingness and capacity of the community to perform operation, maintenance, and disposal requirements for each design.
• How much technical knowledge is required to operate the system?
􀂃 Does this knowledge exist within the community?
􀂃 Can people be trained to operate this system?
􀂃 Do people want to be trained?
􀂃 Will trained people remain in the community? (Labor forces can be migratory. Educated people tend to be drawn to urban centers where there are better job opportunities.)
• Are cultural and traditional preferences and taboos considered and respected?
􀂃 Consider how favorite aspects of the current system can be incorporated into the design (location, taste of water, ease of operation, privacy). People are most willing to accept something with which they are familiar.
􀂃 Refer to information gathered during needs assessment
􀂃Ex: Certain sanitation systems may require handling of excreta that may be unacceptable in some cultures.
• When will the system require maintenance? (Daily, monthly, seasonally)
􀂃 Will people have the time to perform maintenance?
􀂃 Will this vary depending on the season? (seasonality of labor)
􀂃 Ex: During the harvest people are very busy and will be unwilling to take on any additional tasks.
􀂃 Can maintenance schedules be timed to coordinate with labor availability?
BACK | □ Design recognizes and respects traditional gender roles.
• Women are often in charge of household water supply, while men are involved in construction and technology. Will a new system interfere with the traditional gender power balance?
• What will be the role of men and women in the new system?
• How can the project encourage ownership by both gender groups?
• Are separate facilities provided for men and women if necessary?
BACK | □ Recognize why biases exist towards certain technologies by donors and/or locals.
• Are certain improved systems associated with prestige and wealth?
• Are there political pressures/incentives to adopt certain technologies?
• Are some systems more acceptable because of their familiarity to either residents or donor agencies?
• What significance is placed on system convenience, privacy, comfort, or aesthetics?
• Are there differences in cultural standards of quality or cleanliness that need to be reconciled?
• Remember that not all biases are negative. Some may be helpful in promoting the use and general acceptance of the system.
BACK | □ The project goals are clearly defined and understood by the community and development workers.
• What need had the highest priority?
• How do community members visualize the expected benefits? How do the development workers?
􀂃 Increased health?
􀂃 Increased incomes?
􀂃 Reduction in seasonal migrations?
􀂃 Time and labor savings?
• Who will benefit from the project?
􀂃 Will all members benefit equally?
􀂃 Are all the beneficiaries represented in community discussions?
• Are community members and development workers in agreement?
BACK | □ Identify a representative committee that can act as the community liaison throughout the project.
• Can this committee present the community opinions and views to the project planners?
• Will they be responsible for reporting project plans back to the community, including explanations of alternatives?
• Is the committee capable of performing (or assigning the responsibility for) the following roles?
􀂃 Assisting in feasibility studies
􀂃 Gathering of field data
􀂃 Organizing community education
􀂃 Generating support for the project.
• Can an existing committee fill this role?
• Is it necessary to create a new committee? (Note: there is a danger of too many committees within a community. It can lead to a confusion of roles.)
• Does this group represent all beneficiaries? (men, women, ethnic diversity)
• Are members of this committee respected within the community?
• Does this committee operate according to local customs?
BACK | □ Present several technically feasible alternatives for community evaluation and feedback.
• Does the presentation of each design include a technical description, estimated costs, installation time, and operation and maintenance needs?
• Is the potential for long-term management of each system emphasized?
• Are presentations of alternatives done in a fair and balanced way?
• Does the community understand the proposed technology?
• Are advantages and disadvantages of each design understood and discussed?
• Does the community think that they can manage and maintain the system on their own?
• What education, training or support services would be necessary for the proposed designs?
• Are there any community concerns not addressed in the conceptual designs?
• Are there legal issues surrounding use of the water source or necessary land?
• Is there sufficient knowledge within the community to manage the systems being considered?
BACK | □ Community members formally select a design based on an understanding of the constraints involved in the selection process.
• Are community members allowed to judge the advantages and disadvantages of differing systems?
• Are decision-makers given time to reflect before selecting a design?
• How is the decision reached? Democratic process? Leader decides?
• Is this process consistent with traditional methods of community decision making?
• Is the decision influenced by outside forces?
• Is it possible to judge if the design was chosen on technical merit or political motivation?
• Do community members seem happy with the selected design?
BACK | □ Develop a working relationship with partner organization(s), including at least one that is based in the host country.
• Have local government officials, NGOs, or private enterprises been contacted?
• Do partner organizations have compatible programs and agendas?
• What is the expected level of support and interaction from all parties?
• Do partners have suggestions or feedback on the designs?
• Are government officials kept informed?
• Can the basic goals of the working relationship be written in a Memorandum of Understanding (MOU)? (EWB, 2005)
BACK | □ Consult the plans and designs of other organizations on similar projects.
• Have similar projects been implemented in the area?
• Will the project be redundant or in conflict with another project?
• What technical designs are working in nearby communities?
• What constraints did they use?
• Were there problems? How were they resolved?
• How long did the projects take?
BACK | □ Explore options to integrate existing technologies or programs into conceptual designs.
• What water supply and sanitation technologies are being promoted by government or NGO programs in the area?
• What is the potential to use these technologies in the design?
• Could other programs offer education or training support?
• Are there institutions pushing health initiatives that could provide educational services and support?
BACK | □ Contact potential partner institutions for project financing.
• Are there grants or low-interest loans available?
􀂃 For agencies?
􀂃 For individuals?
• What are the conditions for receiving funding?
• Are funds available for operation and maintenance?
• Are programs and funding available for supportive health/sanitation education?
BACK | □ Estimate the implementation costs of each conceptual design.
• Are training costs included?
• How much will materials and equipment cost?
• What local materials can be used? What will it cost?
• How can non-local materials be obtained?
• What will transportation of materials, equipment, and laborers cost?
• What will labor cost? Skilled and unskilled?
• Will food be provided for labor crews? What will it cost?
• Can community members provide local cost information?
• Will there be political fees that should be included in the budget?
• How should development workers’ time be included?
• What about costs for promoting use of the system or health education?
BACK | □ Estimate operation, maintenance, and disposal costs for each conceptual design.
• Include costs for materials, replacement parts, and skilled laborers.
• Can these parts and materials be found locally?
􀂃 If not, include cost estimates for transportation of supplies or displacement of people to get supplies
• How often will materials and parts need replacement?
• What are the minimum costs to keep the system running?
􀂃 Daily
􀂃 Weekly
􀂃 Monthly
􀂃 Annually
• How will recurrent costs be recovered?
􀂃 Fees
􀂃 Outside aid
BACK | □ Assess the community willingness-to-pay in both monetary and non-monetary terms for each improved system. There are a number of methods in use for determining willingness-to-pay: contingent valuation surveys, estimations based on a percentage of income or current expenditures. (Goldblatt,1999: Raje et al., 2002: Whittington et al., 1991/1990) The community willingness to pay should be determined on more than a “rule of thumb” based on a percentage of household income. It should be voiced by community members themselves, either directly in interviews or indirectly by costs that they currently pay for services.
• What do people pay for water and sanitation services?
• What is considered an adequate level of service?
• How much money are people willing to pay to obtain this service?
􀂃 Construction/Implementation fee?
􀂃 Monthly?
􀂃 Yearly?
􀂃 Per use?
BACK | • What are people willing to contribute to construction and start-up capital costs?
􀂃 Monetary
􀂃 Non-monetary items
􀂃 Are people willing to work to obtain this service? (labor, supplies, construction material, tools)
• What are people willing to pay to maintain an improved system?
􀂃 Indirectly: service fees
􀂃 Directly: labor for maintenance or repairs, replacement parts or materials
BACK | □ Conduct an economic feasibility assessment to evaluate long-term project viability based on cost estimates, projected operation and maintenance costs, community willingness to pay, the need for outside resources, and the availability of outside funding.
An economic feasibility assessment is suggested in place of a traditional cost-benefit analysis. In international water and sanitation projects, benefits are often hard to quantify. There are data limitations that make it difficult to estimate the health and economic benefits that would traditionally be used to justify costs. The larger question in developing countries is the sustainability of the project. The measurable benefits will be negligible if the project is not maintained. In fact, sanitation systems such as latrines can have negative health impacts if they are not properly cleaned and used (Pickford, 1995). An economically sustainable project is one that offers long-term benefits (i.e. remains in operation) at an affordable price. The definition of an affordable price will be determined by what beneficiaries and government officials are willing to pay. There are many methods for determining the community willingness to pay (see above). Willingness to pay on the part of the government (or other aid organizations) can be determined based on the amount of grants, subsidies, or other funding currently directed at water and sanitation systems (see element 2,3).
In an economical feasibility assessment, the project viability is determined by weighing cost estimates for construction, operation and maintenance, versus the willingness of the government and community to pay for it. For example, an unsustainable project may have sufficient funding and community support to construct the system, but operational costs exceed what the community and aid institutions are willing to pay. Decision makers will have to evaluate the long-term viability of the project based on the gap between anticipated support and expected costs.
• What is the total cost to implement the project?
• What can the community contribute to these costs?
• What funding is available to implement the project?
• What is the estimated start-up cost?
• What are realistic estimations of operation and maintenance costs? Note the danger of investing more money up front (high technology) to avoid operation and maintenance costs. The high cost of fixing these systems when they do require maintenance (and they will) may be quite inhibitory (Howe and Dixon, 1993).
• What is the total annual cost per household (including capital and recurrent costs)? (for more details refer to Pickford, 1995)
• What percentage of this is the community willing to pay?
• Will outside resources be needed for operation and maintenance?
• Will these resources be available?
BACK | □ Assess the capacity for sustainable water use in the geographic area.
• Can the water source provide an adequate supply throughout the year?
• How will use of the water source affect the aquatic ecosystem?
• How will the watershed be protected?
• Will sanitation practices endanger existing water sources?
BACK | □ Consider how seasonal variation in water supply, demand, and environmental conditions will affect each conceptual design.
• Does water availability vary by season?
• How does demand for water vary throughout the year?
• Will evaporation rates affect the project design?
• How much does the water table fluctuate during the year?
􀂃 How will this affect designs for sanitation systems? (latrine depth, septic systems, infiltration rates for soak pits)
􀂃 How will this affect water sources? (necessary well depth, recharge of surface water)
• Is the area subject to flooding?
• How will these variations affect the feasibility and cost of conceptual designs?
BACK | □ Consider land needs and availability of suitable land for each alternative.
• Is the necessary land available?
• Is the available land suitable as a project site?
• Is the available land in a convenient location? How far from users?
• What are the potential repercussions of displacing other land uses?
BACK | □ Conduct a site impact analysis for each alternative.
• How will resource gathering (lumber, aggregate, water) affect the site environment?
• How invasive are proposed construction techniques?
• How will the operation of the system affect the environment? At the site? In surrounding areas?
􀂃 Water contaminant
􀂃 Waste discharges
􀂃 Disposal of used parts and fuel containers (Where? How?)
􀂃 Ecosystem disturbance
􀂃 Resource consumption (fuel, batteries, water, chemicals)
• How susceptible is the site to environmental damage?
• What is the potential for remediation/mitigation of damage?
Planning Stage
BACK | □ Understand the traditional structure of community projects.
• Is there a history of community projects? (people working together for the common good)
• How are community projects traditionally organized?
• Who determines what projects will require community effort? (Local action planners, leaders)
• Who directs the work? (foreman, village chief, committee)
• Who performs the work?
• Are there culturally determined roles that must be respected?
• Do all households contribute? How?
BACK | □ Consider the seasonality of labor in setting the timeline.
• When will laborers be available?
• Consider employment schedules, migratory patterns, planting, harvest, holidays, weather
BACK | □ Explore options for increasing gender equity in project roles and capacity building.
• What role do women traditionally play in community projects?
􀂃 Construction projects
􀂃 Communal agricultural efforts (harvest, planting, irrigation)
􀂃 Operation of water and sanitation services
• What roles do women feel comfortable playing?
• Are there ways to increase the involvement of women in the current project?
􀂃 Ex: Bringing water to the site for mixing concrete or cleaning the work site.
􀂃 Ex: Train them in operation and maintenance
BACK | □ Confirm that labor and resource contributions are equitably divided.
• Among households?
• Among ethnic groups?
BACK | □ Community input is solicited in refining the selected technical design.
BACK | □ Final technical design is approved through a process of community consensus.
BACK | □ Community members are involved in identifying and sequencing tasks that will be incorporated into an action plan.
• What concrete tasks need to be accomplished?
􀂃 Gathering supplies and finances
􀂃 Arranging legal requirements for project work (land/water rights)
􀂃 Storing materials and equipment
􀂃 Recruiting skilled and unskilled laborers
􀂃 Construction work
􀂃 Construction supervision
• Who will be in charge of completing these tasks?
􀂃 Community members or someone from outside the community?
􀂃 Managerial roles (oversight, consulting, informing other of the work, managing resources)
􀂃 Labor roles
• Is there a management system in place?
􀂃 Is there an existing water board or committee?
􀂃 Will it be necessary to establish a governing board for the system?
• When do these tasks need to be completed?
􀂃 Develop a timeline
􀂃 Set a schedule for task completion
• How will the project be promoted in the community?
• Who will receive technical/ operational training?
• Who will receive health education (hygiene, hand-washing, proper use of system)?
• Are assumptions in roles and contributions explicitly stated? (Ex: If community members will provide labor, meals for workers, or tools)
BACK | □ The community members and development workers approve of the timeline and responsibilities laid out in the action plan.
• Are the roles and responsibilities of individuals and organizations explicitly stated?
􀂃 Performing the work
􀂃 Overseeing progress
􀂃 Consulting
􀂃 Informing others of the work
􀂃 Managing resources
• Are all parties aware of their own roles and responsibilities, as well as, those of everyone else?
• Are the skills, knowledge and attitude of individuals factored into role assignments?
• Does the timeline include tasks to be completed by both community members and development workers?
• Does the timeline include dates for the community monetary contribution paid, resource gathering, start of work, expected progress, completion?
BACK | □ The roles and responsibilities of partner institutions are defined in a detailed action plan.
• What level of involvement is each organization willing to commit to?
􀂃 Financial support
􀂃 Consulting
􀂃 Sub-contracting
􀂃 Training and Education
􀂃 Direct community involvement
• What specific reporting or procedural requirements does each organization need?
􀂃 Progress and monitoring reports
􀂃 Contracts
􀂃 Site visits
􀂃 Education or capacity building activities
􀂃 Other paperwork
• Who needs to be informed of project activities?
• Who will supervise the project?
• Who will monitor progress?
• Who will work directly with the community?
• Who will recruit skilled laborers?
BACK | □ Agree on financial commitments.
• Who will contribute to project financing?
􀂃 How much?
􀂃 When will funds be available?
• Who will control the project budget?
• What strings are attached to institutional funds?
􀂃 Earmarks
􀂃 Reporting requirements
BACK | □ A timeline is drafted that meets the requirements of all institutions involved.
• What are the funding and reporting schedules of the institutions?
• When will work start?
• When are progress and final reports due?
• When will work be completed?
• Are institutional deadlines respected?
BACK | □ Final project design and action plan are presented to partner institutions and local, regional, and/or national level authorities.
• Are all parties aware of their role and the timeline agreed upon?
• Have all parties seen the finalized design? (Even if they are not directly involved, they appreciate being informed.)
BACK | □ Verify the costs and availability of resources.
• Present an itemized budget for review by community members (they understand the local market)
• What are the local prices?
• Do they fluctuate? By how much? (It is best to verify prices as close to the purchasing time as possible)
• What is the currency conversion rate in the country? (Check the rate on the open market as it can differ from the official rate)
• Can anything be improvised or constructed on site?
• What about transportation costs?
• What do laborers cost? Unskilled? Skilled?
• Does the cost of labor vary depending on the time of year? (issue of availability)
• Are costs for training included in the budget?
BACK | □ Confirm the community contribution for money, materials, equipment, tools, and labor.
• Who will provide the monetary contribution? How much?
• Who will provide tools and equipment?
• Is there a storage area for large tool and construction supplies?
• How many laborers can the community contribute?
• Will meals be provided for laborers? By whom?
• Who will provide for food and housing for trainers from outside the community?
• Are individual contributions consistent with their ability to pay?
• The community makes a formal commitment to the agreed contribution.
BACK | □ Finalize budget based on local costs, available resources, and community contribution.
• Include a contingency plan for unexpected costs.
• Can the budget adjust for alternative plans if required materials become unavailable?
BACK | □ Develop an action plan for resource procurement.
• When will materials be required throughout the construction process?
• Where will materials be purchased? By whom? When?
• How will they be transported to the site?
• Is manufacture of materials required?
􀂃 Ex: breaking rocks into gravel or blacksmithing of parts
􀂃 How long will it take?
􀂃 How far in advance can it be performed?
• Are skilled laborers required?
􀂃 When are they available?
􀂃 Is a signed contract required?
• Who will arrange for unskilled laborers?
BACK | □ The final project design minimizes ecological disturbance, energy use and waste emissions.
• How different is the final design from the conceptual design? Does the site impact assessment still hold true?
• Have all environmental impacts been considered during the design process?
• Have efforts been made to reduce these impacts?
• Is energy saving technologies used?
• Are secondary treatment options implemented where appropriate?
• Are there methods for monitoring environmental impacts during the project life?
BACK | □ The project design uses renewable and/or recyclable local resources.
• Are local alternatives to imported materials considered during the design development?
• Are these resources abundantly available?
BACK | □ The action plan considers the seasonality of resources.
• When is the site or resource accessible?
􀂃 Will flooding affect site accessibility; by boat, by road?
􀂃 Ex: Sand may only be available when the rivers are low.
• Will the size, availability, and productivity of the labor pool vary with the season?
• What time of year is best for construction?
􀂃 Rain
􀂃 Temperature
BACK | □ Develop an environmental action plan to mitigate impacts during construction.
• Use of erosion control techniques
• Consideration of temporary water sources
• Non-invasive construction methods
• Waste disposal
• Site restoration needs after construction
Implementation Stage
BACK | □ Set a realistic work schedule, based on available resources and preferred work styles.
• What is a typical work day?
• What time do communal work projects normally start? And finish?
• What are expectations for breaks and meal times?
• Are there certain days of the week that work can not be performed?
􀂃 Religious observances
􀂃 Markets
• Are there conflicting labor demands (harvest, planting, regular jobs) that affect the availability of personnel?
• How will the availability of equipment limit work?
􀂃 Ex: How many shovels are there? (It will limit the number of workers at one time.)
BACK | □ Scheduling includes float time to allow for unexpected.
• Is time allowed for unplanned social functions such as, funerals, soccer games, or religious observances?
• What are the consequences of not planning for unexpected events?
􀂃 Incomplete project requirements
􀂃 Going over budget
􀂃 Angering people by working through social events
􀂃 Conflicts between development workers and community members
BACK | □ Scheduling includes float time to allow for unexpected.
• Can they collect sand and gravel? Or sift the sand and gravel?
• Can they bring water to the construction site?
• Can they fill management roles?
• Are they included in capacity building exercises? (Including technical and managerial skills.)
BACK | □ Use public gatherings to review benefits of the project, promote education, and discuss operation and maintenance.
• Are all project beneficiaries included?
• Can the project functions and benefits be demonstrated?
• Are project updates given?
• Can hygiene education or other health topics be presented?
• Can people be trained in health education?
• Can this time be used to plant the seeds of operation and maintenance requirements and organizational needs?
BACK | □ Involve the community in revisions of the action plan, program changes, and problem solving.
• Is everyone aware of their responsibilities?
• Do development workers meet regularly with community leaders to review the action plan and program changes?
• Are mid-way evaluations and progress monitoring conducted?
BACK | □ Work with a local foreman or work supervisor in organizing labor.
• Can a local representative help with the following activities?
􀂃 Organize procurement and storage of materials and equipment.
􀂃 Manage work crews and daily construction activities.
􀂃 Daily briefing on the task to be accomplished.
􀂃 Monitor and correct public safety concerns.
BACK | □ Train local laborers in any new techniques and tools that are introduced.
• Can health and hygiene education be included in the training?
• Does the training include construction techniques and procedures for operation and maintenance?
• Can operation personnel be selected from laborers who show the most aptitude for the system?
BACK | □ Finalize the management plan with respect to the “built” system.
• Is the community given complete specifications for the equipment and operating system, including manuals and specific training for operation and maintenance?
• Are community members involved in planning for operation and maintenance?
• Is responsibility for the system officially transferred to community?
BACK | □ Contact institutions in the area for assistance in training and labor requirements.
• Do they have training instructors who speak the local-language?
• Can they provide technical training or supportive education programs?
• Do they have skilled laborers for hire?
• Can they benefit from involvement in the project? (shared trainings)
• Are partner institutions invited to be involved in training exercises?
BACK | □ Inform partner institutions of the start of construction, project milestones and major changes.
• Are progress reports and evaluations shared?
• Is consideration given to how major changes in the design or implementation schedules may affect partner interventions or the government regulatory processes?
BACK | □ Invite local government and NGO officials to view the construction site.
• Are the “right” officials invited?
• Are efforts made to include everyone that could be interested or have a stake in the project?
BACK | □ Discuss partner roles in operation and maintenance.
• Is agency involvement necessary?
• What role can government and donor agencies play in operation and maintenance of the system?
􀂃 Monitoring and evaluations
􀂃 Promotional activities
􀂃 Financial support
􀂃 Providing training and/or payment for maintenance personnel
􀂃 Equipment or support services
􀂃 Ex: Can the municipality (or private company) provide vacuum tanker trucks for emptying latrines?
􀂃 Ex: Can they train technicians to fix the hand pumps next to the community wash area?
• Do partner agencies have the capacity to address these roles?
• Do other agencies need to be recruited to help with operation and maintenance issues?
• Can a tentative agreement be made on an action plan for system operations?
BACK | □ Community members contribute to project implementation.
• Are resources (monetary or non-monetary) collected prior to the start of construction?
• Is labor for construction provided?
• Is someone keeping track of all contributions? (cash, labor, food shelter, land, materials, and water rights)
BACK | □ Recheck the quality of materials and equipment during resource procurement.
• How sturdy are the tools? Can the hold up under strong use?
• What is the quality of the aggregate? Is it acceptable? Does it require cleaning/sifting?
• Are better quality options available? What will they cost?
• If not, will the design need to be modified?
BACK | □ Monitor spending and budget restrictions throughout the project implementation phase.
• Is someone keeping track of when material and equipment purchases are over budget?
• Is a reliable person or committee is in charge of gathering and keeping track of resources?
• Can a respected community member with accounting experience (i.e. village treasurer) be used?
• Are they able to keep records of resources, collect receipts, and arrange for the storage of materials?
• Is a culturally appropriate system of accountability discussed?
• Is a responsible party in charge of labeling and storing spare parts after construction?
• Are procurement and construction schedules processing on-time?
• Are extra fees required to keep the project on schedule?
• Can the budget be adjusted to accommodate for changes?
• How much can the contingency plan cover?
• Are options to improvise tools and equipment explored when necessary?
BACK | □ Draft final report on the budget and share with community members and partner organizations.
• Are final costs calculated?
• Is an itemized list of community contributions and their cash equivalents included? Is it shared with community?
• Are financial repayment schedules reviewed? (if individual or community loans were used to finance the project)
BACK | □ Recheck physical and environmental constraints used in the project design and make design corrections if necessary.
• Groundwater levels
• Soil infiltration rates
• Soil conditions
• Temperature
• Stream and river flow rates
• Evaporation rates
BACK | □ Take precautions to avoid contaminating existing water resources and minimize environmental impacts during implementation.
• Are erosion control methods used during resource extraction (sand, gravel, rock, timber) and construction?
• How can energy or fuel use be reduced? (transportation, extraction needs)
• Can the transport of materials (esp. of heavy equipment) be minimized?
• Can packaging be recycled?
• Are wells covered near the construction sites?
• Are temporary water sources and/or sewage disposal methods used?
BACK | □ Involve the community in waste management and environmental education.
• Are there plans to properly dispose of any waste that is produced?
• Are efforts made to minimize solid waste and energy use?
• Can community members implement the waste management plan?
• Are community members educated on waste management practices?
• Can other environmental issues be discussed?
• Can down time during construction be used for informal education sessions?
BACK | □ Restore any areas disturbed during construction.
• Is the site cleaned-up after construction?
• Are disturbed ecosystems restored?
• Is maintenance of these areas needed and planned for?
Operation, Maintenance, and Evaluation Stage
BACK | □ Discuss unanticipated constraints to system use.
• Why do people not use the system?
􀂃 Distance from home
􀂃 Latrines are full
􀂃 Insufficient water
􀂃 Inconvenient operating schedule
􀂃 Unwillingness to pay
􀂃 Smell or insects
• Is the system being used properly?
􀂃 Is it cleaned?
􀂃 Is it used for the intended purpose?
􀂃 Ex: latrines: Are they being overloaded with water or additional waste? Is the use of twin pits alternated?
• Did people receive instruction on proper use of the system?
BACK | □ Discuss unexpected limitations to maintenance schemes.
• Did people trained in system maintenance leave the community?
• Is performing maintenance seen as shameful or dirty work?
• Are there traditions, taboos, or fears that were overlooked in project planning?
􀂃 Ex: Cultural unwillingness to handle excreta (even when decomposed)
BACK | □ Reassess how gender roles affect the proper use and perceived benefits of the system.
• Are both men and women aware of proper operating rules?
• Have both men and women adopted appropriate behavior changes?
􀂃 Ex: A study in Ghana found that men had changed their latrine habits due to a hygiene education program, but women, who were not involved, kept up bad practices (Pickford, 1995).
• Who cleans the system?
􀂃 Ex: Study of latrine cleanliness in Dar es Salaam found that conditions were better when the male head of the household cleaned rather than a wife or child (Pickford, 1995).
• How can differences be addressed?
BACK | □ Ensure that costs and benefits are equitably distributed within the community.
• Are equitable user fees and operating rules agreed on within the community?
• Do community members have equal access or opportunity to receive services?
􀂃 Ethnic groups
􀂃 Gender
􀂃 Income groups/Casts
BACK | □ Community members are actively involved in performing the necessary operation and maintenance.
• Are the operation/maintenance tasks handles locally?
• Has staff been trained?
• Are operation/maintenance requirements documented and available to the community?
• Is a transition plan in place to train replacement staff?
• Are continuing training plans in place?
• Are operation/maintenance responsibilities clear?
BACK | □ Conduct a participatory evaluation to get community feedback and suggestions for improvements.
• Are a variety of community members involved in the evaluation?
• Was the project perceived as a success? Why? Why not?
• How can system functioning be improved?
• How can utilization of the facilities be improved?
• Were their suggestions for improvements taken into account on the existing system?
• Does the feedback provide suggestions for improving future projects?
BACK | □ A community organization exists with the capacity to make decisions regarding the operations and maintenance of the system.
• How will the community contribute to system maintenance?
• Who will take care of preventive maintenance, and repairs?
• Can the community control who is hired to operate and maintain the system?
• Is an attendant necessary to oversee the system (i.e. public water taps or latrines)?
• How will the attendant be paid?
• Who collects fees?
• Who will keep records and accounting reports?
• Can the community implement suggestions for improvement?
• Can the organization contact other agencies for help if needed?
BACK | □ The system is controlled by culturally appropriate and traditionally respected people.
• Do community leaders determine roles and responsibilities of an oversight committee?
• How are operation and maintenance managers selected?
• Are they selected for their dedication and dependency? Or political reasons?
• Is the oversight committee susceptible to elite capture?
BACK | □ Invite officials to the opening ceremony.
• Are all participants from planning and implementing stages included?
• Are appropriate local and regional officials included?
• Is credit and thanks given to all who helped?
BACK | □ Coordinating institutions sign a formal agreement that defines their roles and expectations in operation and maintenance of the system.
• What roles will government and donor agencies play in operation and maintenance of the system?
􀂃 Monitoring and evaluation reports
􀂃 Promotional activities
􀂃 Financial support
􀂃 Providing training and/or payment for maintenance personnel
􀂃 Equipment or support services
• Who will fill these roles?
• How often are services or support expected?
BACK | □ A locally based institution is involved in project monitoring.
• Do they double-check/monitor technical aspects?
• Can they help in refining management structures?
• Do they keep in touch with any changes in local practice?
• Are partners contacted for follow-up and adjustments if problems arise?
• Do they reach out to regional peers to share knowledge and resources?
BACK | □ Share monitoring reports and project evaluations with partner institutions.
• Are periodic reports on operations and maintenance shared?
• Are financial report shared, if appropriate?
BACK | □ Estimate realistic, long-term operation and maintenance costs based on the “built” system.
• Are costs for materials, replacement parts, and skilled personnel included?
• What labor efforts are needed to keep the system running?
􀂃 Cleaning
􀂃 Emptying for latrines
􀂃 Oiling of mechanical parts
􀂃 Repair of supply lines, tanks, and other physical structures
• How often will materials and parts need replacement?
􀂃 Chemicals for water treatment
􀂃 Spare parts
• Where will replacement materials and parts be purchased?
• What about transport costs?
• What are the minimum costs to keep the system running?
􀂃 Daily
􀂃 Weekly
􀂃 Monthly
􀂃 Annually
BACK | □ Financing exists to cover projected operation and maintenance costs.
• Are there monetary needs to keep the system running? Labor needs?
• How will these needs be met?
􀂃 User fees
􀂃 Community taxes
􀂃 Labor contributions
􀂃 Institutional aid
• What is an appropriate fee for use? What are people willing to pay?
• Who collects the fees?
• Who will provide labor for upkeep and repairs?
• Is outside aid provided?
• Are there mechanisms for getting outside aid if needed?
• Are there options for cost recovery?
􀂃 Ex: Sale of latrine waste for fertilizer
􀂃 Ex: Raising fish in irrigation ponds
BACK | □ A financial management organization exists to manage operational/maintenance costs and the distribution of benefits.
• Does this organization have the capacity to collect and account for monetary contributions? Labor contributions?
• Can it keep track of the beneficiaries?
• Is there a correlation between payments and benefits received?
• Is this organization controlled by the community?
• Is the role of this organization recognized and respected at all levels of governance?
• Is the organization appropriate to the project size and community?
BACK | □ Regularly review and adjust the financing system.
• Is the financing system reviewed on a regular basis?
• Can it be adjusted for inflation and changes in resource availability?
• Can it adjust for changing demands and perceptions of the project benefits?
• Can it adjust for social constraints (non-payment of fees, under/over utilization)?
• Can fees/labor needs be changed?
• Can support from partners be adjusted?
BACK | □ Minimize, treat, and dispose of waste properly.
• Is there waste resulting from the use of the project?
• Is waste properly treated?
• Is the creation and disposal of project related waste monitored and reported?
􀂃 Wastewater
􀂃 Runoff water/Grey water
􀂃 Used parts and equipment
• Are monitoring reports and treatment procedures checked by a managing organization?
BACK | □ Explore alternative plans for reducing the use of consumables.
• What consumables are used during operation/maintenance of the project?
􀂃 Chemicals in water/sanitation treatment
􀂃 Spare parts
􀂃 Fuel/Batteries
􀂃 Plastics (PVC, liners, bottles)
􀂃 Filters
􀂃 Packaging
• Are there ways to reduce the amount of material consumed?
• Are alternative sources of parts, materials, or energy periodically explored?
• How does usage of consumable parts and energy compare with similar projects?
• Are potential alternatives tested?
BACK | □ Monitor and evaluate environmental impacts.
• Is the site periodically surveyed to check for impacts?
• Is a methodology in place for impact assessments?
• Are secondary impacts considered?
􀂃 Does an improved water supply change disposal habits for grey water? Where? How much?
􀂃 If water sources are closer to home, does it bring sanitation problems closer to home?
􀂃 Are there runoff problems around the tap stands?
􀂃 Are people using more water now than before?
• Are the systems functioning properly?
􀂃 What are the environmental impacts if the system malfunctions?
􀂃 Sanitation systems in particular can have negative impacts if not properly maintained.
• Were restoration areas restored properly? And maintained?
􀂃 If trees were replanted, are they watered?
􀂃 If water was diverted from a source, is there enough overflow water to maintain the stream habit?
BACK | □ Continue environmental and hygiene education efforts.
• Are community member aware of improvements since the system became operational? Or deterioration?
• Are supporting behavioral changes reinforced? (hand washing, proper trash and grey water disposal)
• Do people understand the benefits of improved systems?
• Are people motivated to continue to work for environmental improvements?
• Are people aware of their own role in maintaining a healthy environment?

## H-UI
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Help: Inputs Summary
ACTIONS
Main: Setup
INPUTS | Community Name: The name of the community where the water system is to be built.
Community Municipality / County: The municipality or county where the community is located.
SOURCES | Community State / Province: The state or province where the community is located.
Country: The country where the community is located.
Project Title: Enter the name of the project.
Engineer Name: Enter the name of the lead engineer on the project.
Organization Name: The name of the organization overseeing the project.
Organization Address: Address of the overseeing organization.
BACK | Feasibility: Inputs
Community Population: The number of inhabitants within the community to be served by the water system.
Water Source Type: The type of water source that will be used (spring, stream, mix etc.).
Number of Individual Sources to Be Utilized: How many different water sources will be connected to the water system.
Total Flow Rate from Sources: The total flow rate in Liters per second from all the sources to be used.
Source Elevation: The elevation of the water source, if multiple sources are to be used, state the lowest. If absolute elevations are not known, the elevation difference between the source and the community can be entered.
Distance to Source: Distance to the water source in meters.
Network Length in Community: Estimated length of distribution network throughout the community in meters.
Highest Pt. Served In Community: Elevation of the highest point in the community that will be served by the water system.
Lowest Pt. Served In Community: Elevation of the lowest point in the community that will be served by the water system.
Area Soil Type: The type of soil found in the area. This is used to estimate work rates.
Number of Days per Week Labors Can Work: How many days per week will labors be able to work on the water system.
Number of Months per Year Available for Work: How many months of the year are available to work on the water system.
Monthly Community Contribution per Family: How much can each family pay per month to the water system.
Total Funding Available For Project: An estimate of the funding available for this project (If Avaiable)

## H-SU
| MAIN |  | FEASIBILITY | DESIGN | PLANNING | IMPLEMENTATION | EVALUATION | OPTIONS | HELP
HOME |  | Help: Usefull Refrences
ACTIONS
Agua Para La Vida. 2007. APLV Publications and Tools. http://www.aplv.org/New/en/techresources.shtm (Accessed November 30, 2007). Agua Para La Vida and Logilab. 2007. NeatWork - Water Distribution Network. http://www.ordecsys.com/neatwork/ (Accessed November 30, 2007). Alperovits, E., and U. Shamir. 1977. Design of Optimal Water Distribution Systems. Water Resources Research 13, no. 6:885-900. Barnes, Rebecca, and Nicholas Ashbolt. 2006. Review of Decision Tools and Trends for Water and Sanitation Development Projects. In Sustainable Development of Water Resources, Water Supply and Environmental Sanitation, 187-194, Colombo, Sri Lanka. Batteson, Helen, Kay Davey, and Rod Shaw. 1998. DFID Guidance Manual on Water Supply and Sanitation Programmes. London, UK: WELL Publications. Bentley Systems, Inc. 2007. Water distribution modeling and management – WaterCAD for Bentley's Haestad Methods. http://www.bentley.com/en-US/Products/WaterCAD/ (Accessed November 30, 2007). Bolt, E, and C. Fonseca. 2001. Keep it Working: A Field Manual to Support Community Management of Rural Supplies. Delft, The Netherlands: IRC-International Water and Sanitation Center. Brikké, F., and J. Rojas. 2001. Key Factors for Sustainable Cost Recovery in the Context of Community-Managed Water Supply. Delft, The Netherlands: IRC-International Water and Sanitation Center. Cairincross, S. 1992. Sanitation and Water Supply: Practical Lesson from the Decade. London, UK: London School of Hygiene and Tropical Medicine. Carmichael, S., D. Forsyth, and D. Hughes. 2001. Decision support system for the development of rural water supply schemes. South Africa: Water Research Commission. Churchill, Cameron J., and Brian W. Baetz. 1999. Development of decision Support Systmes for Sustainable Community Design. Journal of Urban Planning and Development 125, no. 1:17-35. Corcos, Gilles. 2003. Air In Water Pipes, Second Edition (10-2003): A manual for designers of Spring-Supplied Gravity-Driven Deinking Water Rural Delivery Systems. Berkeley, CA: Agua Para La Vida. Corcos, Gilles, and J.-P. Vial. 2004. NeatWork: A user guide. Berkeley, CA: Agua Para La Vida, University of Geneva. Deverill, M., S. Bibby, A. Wedgewood, and I. Smout. 2002. Designing water supply and sanitation projects to meet demand in rural and peri-urban communities. Loughborough, U.K.: WEDC Publications. Economist Intelligence Unit. 2007. Country Profile 2007: Dominican Republic. London, UK: Economist Intelligence Unit. EWB-USA. 2005. Community Development Guidelines. Engineers Without Borders. Goldblatt, M. 1999. Assessing the effective demand for improved water supplies in informal settlements: a willingness to pay survey in Vlakfontein and Finetown, Johannesburg. Geoforum 30, no. 1:27-41. Howard, Guy, and Jamie Bartram. 2003. Domestic Water Quantity, Service Level and Health. Geneva, Switzerland: World Health Organization. Howe, C. W., and J. A. Dixon. 1993. Inefficiencies in water Projet Desing and Operation in the the Third World: An economic perspective. Water Resources Research 29, no. 7:1889-1894. Jordan, Thomas D. 1984. A Handbook of Gravity-Flow Water Systems. London, UK: Intermediate Technology Development Group. Keefer, D., and S. Kahkonan. 2004. Perspective on decision analysis applications. Decision Analysis 1, no. 1:5-24. Lockwood, H. 2004. Scaling Up Community Management of Rural Water Supply. Delft, The Netherlands: IRC-International Water and Sanitation Center http://www.irc.nl/page/8857. Longland, F. 1998. Field Engineering: An introduction to development work and construction in rural areas. London, UK: Intermediate Technology Publications. Mays, Larry W. 1997. Water Distribution Systems Handbook. New York, NY: McGraw-Hill. McConville, Jennifer R. 2006. Applying Life Cycle Thinking to International Water and Sanitation Development Projects: An assessment tool for project managers in sustainable development work. M.S. Research Report, Michigan Technological University. McConville, Jennifer R., and James R. Mihelcic. 2007. Adapting Life Cycle Thinking Tools to Evaluate Project Sustainability in International Water and Sanitation Development Work. Environmental Engineering Science 24, no. 7:963-974. McMaster University. 2007. McMaster University Sustainable Communities Research Group: Downloads. http://www.eng.mcmaster.ca/civil/sustain/downloads.html (Accessed December 3, 2007). Menon, Shashi. 2005. Piping Calculations Manual. New York, NY: McGraw-Hill. Michigan Technological University. 2007. D80 Center Resources. http://www.d80.mtu.edu/Resources.html (Accessed November 30, 2007). Microsoft Corporation. 2008a. Create and use an Excel template - Excel - Microsoft Office Online. http://office.microsoft.com/en-us/excel/HA102188741033.aspx?pid=CH100648111033 (Accessed January 8, 2008). Microsoft Corporation. 2008b. Define and solve a problem by using Solver - Excel - Microsoft Office Online. http://office.microsoft.com/en-us/excel/HP100726911033.aspx?pid=CH100648511033 (Accessed January 8, 2008). Microsoft Corporation. 2008c. Enable or disable macros in Office documents - Excel - Microsoft Office Online. http://office.microsoft.com/en-us/excel/HA100310711033.aspx (Accessed January 8, 2008). Microsoft Corporation. 2008d. Load the Solver Add-in - Excel - Microsoft Office Online. http://office.microsoft.com/en-us/excel/HP100215701033.aspx?pid=CH100870211033 (Accessed January 8, 2008). Mihelcic, James R. 2004. Educating the Future’s Water Professional. Water Environment Technology 16, no. 9:86-92. Mihelcic, James R. et al. 2003. Sustainability Science and Engineering: Emergence of a New Metadiscipline. Environmental Science & Technology 37, no. 23:5314-5324. Mihelcic, James R., E.A. Myre, L.M. Fry, and B.D Barkdoll. 2008. Field Guide in Engineering for Development Workers: Water Supply, Sanitation Systems, and Indoor Air Quality. Reston, VA: American Society Of Civil Engineers (ASCE) Press. Mihelcic, James R., Linda D. Phillips, and David W. Watkins. 2006. Integrating a Global Perspective into Education and Research: Engineering International Sustainable Development. Environmental Engineering Science 23, no. 3:426-438. MWH Soft. 2007. InfoWater: The Most Comprehensive Geospatial water Distribution Modeling and Management Solution for ArcGIS. http://www.mwhsoft.com/page/p_product/infowater/infowater_overview.htm (Accessed November 30, 2007). Olsen, Daniel Richard. 2005. Decision Support System For Rural Water Supply in the Nilgiris District of South India. Master of Applied Science in Civil Engineering, McMaster University. Peace Corps. 2000. Rural Aqueducts and Community Development in the Dominican Republic. Santo Domingo, Dominican Republic: Peace Corps. Peace Corps. 1983. Rural Water/Sanitation Projects, Water For The World. 0005th ed. Washington, DC: Information and Collection Exchange. Peace Corps Center for Field Assistance and Applied Research. 2001. Global Summary and Promising Practices: Water and Sanitation Projects. Washington, DC: Peace Corps. Pham, D.T., and D. Karaboga. 2000. Intelelligent Optimisation Techniques. London, UK: Springer-Verlang. Pickford, J. 1995. Low-Cost Sanitation, A survey of practival experience. London, UK: Intermediate Technology Publications. Purcell, Patrick. 2003. Design of Water Resource Systems. London, UK: Thomas Telford. Raje, D. V., P. S. Dhobe, and A. W. Deshpande. 2002. Consumer's willingness to pay more for municipal supplied water: a case study. Ecological Economics 42, no. 3:391-400. Reed, Brian. 2005. Minimum water quantity needed for domestic use in emergencies. Geneva, Switzerland: World Health Organization. Reents, Nathan W. 2003. Design of Potable Water Supply Systems in Rural Honduras. Report, Michigan Technological University. Rossman, Lewis A. 2000. EPANET 2 Users Manual. Cincinnati, OH: Water Supply and Water Resources Division, National Risk Management Research Laboratory, United States Environmental Protection Agency. Roy, Bernard, Roman Slowinski, and Wiktor Treichel. 1992. Multicriteria programing of water sypply systems for rural areas. Water Resources Bulletin 28, no. 1:13-32. Selener, D., and J. Carvajal. 1999. Participatory rural Appraisal and Planning. International Institute for Rural reconstruction. Socio Economic Unit Foundation, Kerala India. 2007. Socio Economic Unit Foundation, WaterCADE. http://www.seuf.org/html/watercade.html (Accessed December 3, 2007). U.S. Environmental Protection Agency. 2007. EPANET. http://www.epa.gov/nrmrl/wswrd/dw/epanet.html (Accessed November 30, 2007). United Nations. 2002. Report of the World Summit on Sustainable Development (Johannesburg, South Africa, 26 August-4 September 2002). New York, NY: The United Nations. United Nations. 2005. The Millennium Development Goals Report 2005. New York, NY: United Nations. United Nations. 2006. The Millennium Development Goals Report 2006. New York, NY: United Nations. United Nations. 2000. United Nations Millennium Declaration. The United Nations. United Nations Development Programme, and Peace Child International. 2006. Water Rights and Wrongs - A young people's summary of the United Nations Human Development Report 2006. New York, NY: United Nations Development Programme. Walsh, Michael R. 1993. Toward Spatial Decision support Systems in Water Resources. Journal of Water Resources Planning and Management 119, no. 2:158-169. Watkins, Kevin. 2006. Human Development Report 2006 - Beyond scarcity: Power, poverty and the global water crisis. New York, NY: United Nations Development Programme. Whittington, D., D. T. Lauria, and X. Mu. 1991. A Study of Water Vending and Willingness to Pay for Water in Onitsha, Nigeria. World Development 19, no. 2:179-198. Whittington, Dale, John Briscoe, Xinming Mu, and William Barron. 1990. Estimating the Willingness to Pay for Water Services in Developing Countries: A case studey of the use of contingent valuation surveys in southern Haiti. Ecomomic Development and Cultural Change 38, no. 2:293-311. World Health Organization and UNICEFF. 2000. Global Water Supply and Sanitation Assessment 2000 Report. Geneva, Switzerland: World Health Organization and United Nations Childrens Fund. World Resources Institute in collaboration with United Nations Development Programme, United Nations Environment Programme, and World Bank. 2005. World Resources 2005: The Wealth of the Poor - Managing Ecosystems to Fight Poverty. Washington, DC: World Resources Institute. Yates, D.F., A.B. Templeman, and T.B. Boffey. 1984. The Computational Complexity of the problem of determining least captial cost designs for water supply networks. Engineering Optimization 7:142-155. Zachariah, S., and S. Sebastian. 2005. WaterCADE - Community friendly software for designing and estimation of water supply schemes. In 31st WEDC International Conference, 377-380, Kampala, Uganda.
INPUTS
SOURCES

## fa
Action Results
Socio - Cultural Respect | FALSE |  |  |  |  | Community Population | 0 | Water Avaiable | 0 | L | Tank? | Taps? | Tank Q |  | Money | OC
0 | FALSE |  |  |  |  | Source Flow Rate | 0 | Water Required Public Taps: | 0 | L | FALSE | 0 | 0 |  | FALSE | FALSE
| FALSE |  |  |  |  | Source Elevation | 0 | Water Required Private Taps: | 0 | L | FALSE | 0 | 0 |  | FALSE | FALSE
| FALSE |  |  |  |  | Distance To Source | 0
Community Participation | FALSE |  |  |  |  | Network Length in Community | 0 | Flow Rate Avaiable | 0 |  | Type | Dsource | Dtank
0 | FALSE |  |  |  |  | Highest Pt. Served In Community | 0 | Flow Rate Required Public Taps: | 0 |  | FALSE
| FALSE |  |  |  |  | Lowest Pt. Served In Community | 0 | Flow Rate Required Private Taps: | 0 |  | FALSE
| FALSE |  |  |  |  | Area Soil Type | 1
Political Cohesion | FALSE |  |  |  |  | Number of Days per Week Labors can work | 0 | Workers | 0 |  |  | Avaible | 0
0 | FALSE |  |  |  |  | Number of Months Per Year avaiable for work | 0 | Excavation Rate | 0.55 |  |  | Contribution | 0
| FALSE |  |  |  |  | Monthy Community Contribution Per Family | 1 | Total Man-Days Labor Required | 0 | Meters of Trench | 4.5455
| FALSE | [6 empty] | Days Required Per House | #DIV/0!
Economic Sustainability | FALSE | [6 empty] | Days Avaiable In a Year per house | 0
0 | FALSE | [6 empty] | Weeks Required | #DIV/0!
| FALSE | [6 empty] | Weeks Avaiable | 0
| FALSE | [6 empty] | Years Required | #DIV/0!
Environmental Sustainability | FALSE | [7 empty] | Public | Private
0 | FALSE | [6 empty] | Source IC | 0 | 0
| FALSE | [6 empty] | Source OC | 0 | 0
FALSE
0 | [7 empty] | Main Line IC | 0 | 0
Ordinary Soil Excavation | [7 empty] | Main Line OC | 0 | 0
Gravelly Soil Excavation
Boulder Mix Excavation | [7 empty] | Tank IC | 0 | 0
Medium Rock Cutting | [7 empty] | Tank OC | 0 | 0
Hard Rock Cutting
[8 empty] | Network IC | 0 | 0
|  | Q | D | L | H | New H | LS | Network OC | 0 | 0
| Pub S | 0 | 74.7323 | 0 | 0 | 0 | 0 |  |  |  | Avaiable
| Pri S | 0 | 74.7323 | 0 | 0 | 0 | 0 | Total OC | 0 | 0 | 0 |  | 0 | 0
| Pub S | 0 | 71.6227 | 0 | 0 | 0 | 0 | Total IC | 0 | 0 | 0 |  | 0 | 0
| Pri S | 0 | 316.9681 | 0 | 0 | 0 | 0
[8 empty] | Sustainabiity Scocre | 0
| Socio - Cultural Respect | Community Participation | Community Participation | Economic Sustainability | Environmental Sustainability |  |  | ACTIONS
| 0 | 0 | 0 | 0 | 0

## pa
PLANNING- | Action Results
Socio - Cultural Respect | FALSE
0 | FALSE
FALSE
FALSE
Community Participation | FALSE
0 | FALSE
FALSE
FALSE
Political Cohesion | FALSE
0 | FALSE
FALSE
FALSE
Economic Sustainability | FALSE
0 | FALSE
FALSE
FALSE
Environmental Sustainability | FALSE
0 | FALSE
FALSE
FALSE
0

## ia
IMPLEMENTATION- | Action Results
Socio - Cultural Respect | FALSE
0 | FALSE
FALSE
FALSE
Community Participation | FALSE
0 | FALSE
FALSE
FALSE
Political Cohesion | FALSE
0 | FALSE
FALSE
FALSE
Economic Sustainability | FALSE
0 | FALSE
FALSE
FALSE
Environmental Sustainability | FALSE
0 | FALSE
FALSE
FALSE
0

## ea
OPERATION AND MAINTENENCE- | Action Results
Socio - Cultural Respect | TRUE
4 | TRUE
TRUE
TRUE
Community Participation | FALSE
0 | FALSE
FALSE
FALSE
Political Cohesion | FALSE
0 | FALSE
FALSE
FALSE
Economic Sustainability | FALSE
0 | FALSE
FALSE
FALSE
Environmental Sustainability | FALSE
0 | FALSE
FALSE
FALSE
4

## gc
Information Needed for Feasibility Assessment | [9 empty] | LPCD | Users |  | TapStand Flow Rate
[9 empty] | Private Tapstands | 50 | 5 |  | 0.125
[9 empty] | Public Tapstands | 50 | 250
Trial # | Population | Intake Estimate |  | Main Line Estimate |  |  |  | Tank Estimate |  | Network Estimate
|  | IC Source ($$) | OC Source ($$) | L source (m) | ΔH Source (m) | IC Line($$) | OC Line ($$) | IC Tank ($$) | OC Tank ($$) | ΔH Network (m) | L network (m) | IC network ($$) | OC network ($$) |  | V | Qin | Qout
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
Coefficients |  |  | LS Values |  |  | Intake: | [6 empty] | Tank:
α1 | 59338.6624 |  | IC Intake | 0 |  | IC | New IC | LS | OC | New OC | LS |  | IC | New IC | LS | OC | New OC | LS
α2 | 88.3417 |  | OC Intake | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
α3 | 33.37 |  | IC M Line | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
α4 | 33.37 |  | OC M Line | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
α5 | 0.00047046 |  | IC Tank | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
α6 | 8.4658e-07 |  | OC Tank | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
α7 | 90000 |  | IC Network | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
α8 | 0.00094253 |  | OC Network | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
α9 | 4.3853 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
α10 | 4.4308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
α11 | 0.019305 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
α12 | 0.019305
β1 | 0.24485 |  |  |  |  | Main Line
β2 | 0.20432 |  |  |  |  | Diameter | H | New H | LS | IC | New IC | LS | OC | New OC | LS
β3 | 0 |  |  |  |  | 16.0415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
β4 | 3.1884 |  |  |  |  | 33.8012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
β5 | 0.0017192 |  |  |  |  | 28.0126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
β6 | 0.64108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
β7 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Network Line
[6 empty] | Diameter | H | New H | LS | IC | New IC | LS | OC | New OC | LS
[6 empty] | 64.6499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 104.1816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 55.8361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0